## Status Summary
Project Dashboard
Note: Project plan with original dates and actual dates should be attached. | [6 empty] | Date: | 2016-02-18
Project Name: | Got your Back | [5 empty] | Project Status: | G
Project Description: | Our system, known as “Got Your Back,” utilizes Google Glass to solve one of the biggest dilemmas of today’s society: creating transparency between law enforcement and society while providing a new level of safety for police officers.
Customer | Philadelphia Police Force
Project Core Team: | Peter Hwang, Steve Scanlon, Ashley Lombardo, Jack Portnoy
Next Milestone: | Begin Prototyping
Phase Status
| Status | Plan |  | Status | Plan |  | Status | Date
Analysis | G | 2016-01-26 | Testing | Y | 2016-03-22
Design | G | 2016-02-23 | Installation | Y | 2016-04-05
Construction | G | 2016-03-08
Leading Indicators | Status |  |  | Status |  |  | Status
On-Time | G | On-Budget |  | G | Delivery to Scope |  | G
Major Accomplishments/Decisions
We met and interviewed Campus police and Charles Leone, Executive Director of Public Safety at Temple University, in order to truly understand our end users. They gave us great insight and the next steps to actually implement Got your Back.
CURRENT KEY ACTIVITIES --- NOTE ACTUAL (VS PROJECTED) DATES ARE INDICATED BY ITALICS
|  |  |  | START |  |  | END
Current Key Activities | STATUS |  | PHASE | PLAN | ACT | Comments | PLAN | ACT
Create plan | G | Analysis |  | 2016-01-19 | 2005-02-01 |  | 2016-01-16 | 2016-01-16
Project Charter | G | Design |  | 2016-01-19 | 2016-02-01 |  | 2016-01-16 | 2016-01-16
Prototype | Y | Design |  | 2016-02-16 | 2016-02-16 |  | 2016-02-26 | 2016-02-26
Key Issues
Description |  | Status | Resolution/Update |  |  |  | Owner
Only 1 prototyper |  | Y | Only one group member has experience prototyping a full project |  |  |  | Steve
Privacy issues |  | Y | We have to figure out privacy issues of officerswith glasses inside homes |  |  |  | All
Business Case |  | Y | Figure how we'll acquire our first customers |  |  |  | Ashley
Process and System |  | Y | Figure out the system and process for Got Your Back |  |  |  | All
Planned Accomplishments
Since now we have more information on the end user, we plan on figuring out the process and system required of Got Your Back. After a system and process is created, we plan starting the prototype. We didn't want to start the prototype without first figuring out the system and process.
Note on B46: Key Issues are issues that need your CM Director-level understanding and awareness.