## Status Summary
Project Dashboard
Note: Project plan with original dates and actual dates should be attached. | [6 empty] | Date: | 2016-03-07
Project Name: | Got your Back | [5 empty] | Project Status: | G
Project Description: | Our system, known as “Got Your Back,” utilizes Google Glass to solve one of the biggest dilemmas of today’s society: creating transparency between law enforcement and society while providing a new level of safety for police officers.
Customer | Philadelphia Police Force
Project Core Team: | Peter Hwang, Steve Scanlon, Ashley Lombardo, Jack Portnoy
Next Milestone: | Prototype Beta
Phase Status
| Status | Plan |  | Status | Plan |  | Status | Date
Analysis | G | 2016-01-26 | Testing | Y | 2016-03-22
Design | G | 2016-02-23 | Installation | Y | 2016-04-05
Construction | G | 2016-03-08
Leading Indicators | Status |  |  | Status |  |  | Status
On-Time | G | On-Budget |  | G | Delivery to Scope |  | G
Major Accomplishments/Decisions
We have begun the prototype and it is in its first stage of completion. We look to add more detail and options in the upcoming phases, but currently have the backbone of the prototype in place.
CURRENT KEY ACTIVITIES --- NOTE ACTUAL (VS PROJECTED) DATES ARE INDICATED BY ITALICS
|  |  |  | START |  |  | END
Current Key Activities | STATUS |  | PHASE | PLAN | ACT | Comments | PLAN | ACT
Create plan | G | Analysis |  | 2016-01-19 | 2005-02-01 |  | 2016-01-16 | 2016-01-16
Project Charter | G | Design |  | 2016-01-19 | 2016-02-01 |  | 2016-01-16 | 2016-01-16
Prototype Alpha | G | Design |  | 2016-02-16 | 2016-02-16 |  | 2016-02-26 | 2016-02-26
Prototype Beta | Y | Design |  | 2016-03-15 |  |  | 2016-03-20
Key Issues
Description |  | Status | Resolution/Update |  |  |  | Owner
Only 1 prototyper |  | G | Only one group member has experience prototyping a full project |  |  |  | Steve
Privacy issues |  | Y | We have to figure out privacy issues of officerswith glasses inside homes |  |  |  | All
Business Case |  | Y | Figure how we'll acquire our first customers |  |  |  | Ashley
Process and System |  | Y | Figure out the system and process for Got Your Back |  |  |  | All
Planned Accomplishments
We are planning the next state of our prototype so that our full idea comes to reality. We are looking to add certain features and also figuring out the exact system and process that we want to execute for Got Your Back.
Note on B46: Key Issues are issues that need your CM Director-level understanding and awareness.