## Status Summary
Project Dashboard
Note: Project plan with original dates and actual dates should be attached. | [6 empty] | Date: | 2016-04-12
Project Name: | Got your Back | [5 empty] | Project Status: | G
Project Description: | Our system, known as “Got Your Back,” utilizes Google Glass to solve one of the biggest dilemmas of today’s society: creating transparency between law enforcement and society while providing a new level of safety for police officers.
Customer | Philadelphia Police Force
Project Core Team: | Peter Hwang, Steve Scanlon, Ashley Lombardo, Jack Portnoy
Next Milestone: | Finish Documentation, Present
Phase Status
| Status | Plan |  | Status | Plan |  | Status | Date
Analysis | G | 2016-01-26 | Testing | G | 2016-03-22
Design | G | 2016-02-23 | Installation | G | 2016-04-05
Construction | G | 2016-03-08
Leading Indicators | Status |  |  | Status |  |  | Status
On-Time | G | On-Budget |  | G | Delivery to Scope |  | Y
Major Accomplishments/Decisions
Our core prototype is complete and we will continue to work on it to work out any bugs, make updates and make it look aesthetically pleasing. We have already made updates to the baseline prototype to help give it more capabilities. We have also continued to edit and maintain our documents to keep them current with the prototype.
CURRENT KEY ACTIVITIES --- NOTE ACTUAL (VS PROJECTED) DATES ARE INDICATED BY ITALICS
|  |  |  | START |  |  | END
Current Key Activities | STATUS |  | PHASE | PLAN | ACT | Comments | PLAN | ACT
Create plan | G | Analysis |  | 2016-01-19 | 2005-02-01 |  | 2016-01-16 | 2016-01-16
Project Charter | G | Design |  | 2016-01-19 | 2016-02-01 |  | 2016-01-16 | 2016-01-16
Prototype Alpha | G | Design |  | 2016-02-16 | 2016-02-16 |  | 2016-02-26 | 2016-02-26
Prototype Beta | G | Design |  | 2016-03-15 | 2016-03-15 |  | 2016-03-20 | 2016-03-21
Final Prototype | G | Completion |  | 2016-03-22 |  |  | 2016-04-12
Final Presentation | G | Completion |  | 2016-04-01 |  | PowerPoint done, presentation started | 2016-04-08
Key Issues
Description |  | Status | Resolution/Update |  |  |  | Owner
Only 1 prototyper |  | G | Only one group member has experience prototyping a full project |  |  |  | Steve
Privacy issues |  | G | We have to figure out privacy issues of officers with glasses inside the homes of people where a police wearing this technology will enter - although one cannot enter without a search warrant - police will have to offer to turn the camera off when entering homes and hospitals |  |  |  | Ashley
Privacy issues/wasted recording |  | Y | Police departments do not know when to have the camera on and off - it results in wasted video and people not feeling comfortable to talk to police with tips, concerns, etc. |  |  |  | Ashley
Data ownership |  | Y | Who owns this data and how will it be used 5 years down the road? |  |  |  | Ashley
Business Case |  | Y | Figure how we'll acquire our first customers |  |  |  | Jack
Process and System |  | G | Figure out the system and process for Got Your Back |  |  |  | Peter
PowerPoint Presentation |  | G | Finish up the powerpoint presentation with all the required parts. |  |  |  | Steve
Planned Accomplishments
We have a completed plan of the full idea of our prototype. We have added features to really make this application a reality. We figured out the exact system and process that we want to execute for Got Your Back. We plan to put it all together to complete our application once the system and process is exactly how we want.
Note on B46: Key Issues are issues that need your CM Director-level understanding and awareness.

## Compatibility Report
Compatibility Report for Status Report5.xls
Run on 4/5/2016 0:34
The following features in this workbook are not supported by earlier versions of Excel. These features may be lost or degraded when opening this workbook in an earlier version of Excel or if you save this workbook in an earlier file format.
Minor loss of fidelity | # of occurrences | Version
Some cells or styles in this workbook contain formatting that is not supported by the selected file format. These formats will be converted to the closest format available. | 1 | Excel 97-2003