## Status Summary 102317
Project Dashboard
Note: Project plan with original dates and actual dates should be attached. | [6 empty] | Date: | 2017-10-23
Project Name: | Impulse | [5 empty] | Project Status: | Y
Project Description: | Our app will increase the location accuracy and response time for police officers.
Customer | Law Enforcement
Project Core Team: | Tony Nguyen, Siling Zhang, Will Wang, Weiming He
Next Milestone: | Design
Phase Status
| Status | Plan |  | Status | Plan |  | Status | Date
Analysis | G | 2017-09-07 | Testing | Y | 2017-10-08
Design | Y | 2017-09-17
Construction | Y | 2017-10-01
Leading Indicators | Status |  |  | Status |  |  | Status
On-Time | Y | On-Budget |  | G | Delivery to Scope |  | G
Major Accomplishments/Decisions
Continuous work on prototype. We scheduled a webex meeting with our mentor John Wiggs next Monday on 10/30.
CURRENT KEY ACTIVITIES --- NOTE ACTUAL (VS PROJECTED) DATES ARE INDICATED BY ITALICS
|  |  |  | START |  |  | END
Current Key Activities | STATUS |  | PHASE | PLAN | ACT | Comments | PLAN | ACT
Discussion/General Plan | G | Analysis |  | 2017-08-31 | 2017-09-07 | Research on GPS technology on law enforcement | 2017-09-28 | 2017-09-28
Project Proposal | G | Analysis |  | 2017-09-05 | 2017-09-07 | Core Team Meeting | 2017-09-27 | 2017-09-28
Project Charter | G | Analysis |  | 2017-09-12 | 2017-09-21 | Team meeting | 2017-10-10 | 2017-10-12
Project Site and Charter Revision | G | Analysis/Design |  | 2017-09-26 | 2017-09-25 | Mentor meeting | 2017-10-30
Design Prototype | Y | Design |  | 2017-10-17 | 10/15/17
Revised Charter, Prototype, Site | Y | Design |  | 2017-11-14
Presentation | Y | Presentation |  | 2017-12-05
Key Issues
Description |  | Status | Resolution/Update |  |  |  | Owner
Ideas for prototype |  | Y | Meeting scheduled for 10/7. |  |  |  | Project Team
Prototype collaboration |  | R | Meeting in class to discuss |  |  |  | Project Team
Planned Accomplishments
Started prototype work. Scheduled mentor meeting
Note on B46: Key Issues are issues that need your CM Director-level understanding and awareness.