## Status Summary
Project Dashboard
Note: Project plan with original dates and actual dates should be attached. | [6 empty] | Date: | 2016-09-15
Project Name: | Implement a Delivery System for Fresh Grocery Items | [5 empty] | Project Status: | G
Project Description: | Millennial consumers are concerned about the long-term health effects of biotechnology and pesticides. They're looking at down-the-road diseases like cancer, heart disease, obesity and the "unknown." This project will create a direct selling platforms for fruit and vegetable to be delivered from farm to table and give the consumers confidence that safety precautions were taken prior to purchase.
Customer | Joe Smith, Manager, Customer Relations
Project Core Team: | Lamar Dixon, Darryl Jones, Nicholas Stamboolian, Ryan Trapp, and Celynna Zoleta
Next Milestone: | Delivery of Testing plan
Phase Status
| Status | Plan |  | Status | Plan |  | Status | Date
Analysis | Y | 2016-09-27 | Testing | G | 2016-11-17
Design | G | 2016-10-04 | Installation | G | 2016-12-06
Construction | G | 2016-10-20
Leading Indicators | Status |  |  | Status |  |  | Status
On-Time | G | On-Budget |  | G | Delivery to Scope |  | Y
Major Accomplishments/Decisions
Last week at our group project meeting, the team met together to discuss everyone's visions and ideas for the application. There were conflicts in ideas where some teams members had a different approaches to the project, but the team was successfully able to agree on an idea since everyone was open to change and improvements. The end result of this meeting was a clear idea on how to create the application for the food delivery application along with ideas of companies that we could possibly partner up with in the future.
CURRENT KEY ACTIVITIES --- NOTE ACTUAL (VS PROJECTED) DATES ARE INDICATED BY ITALICS
|  |  |  | START |  |  | END
Current Key Activities | STATUS |  | PHASE | PLAN | ACT | Comments | PLAN | ACT
Test plan | Y | Design |  | 2016-09-10 | 2016-09-13 | Project idea conflicts | 2016-09-20 | 2016-09-20
Final project plan | G | Analysis |  | 2016-09-21 | 2016-09-21 |  | 2016-09-27 | 2016-09-27
UI Mockup | G | Design
--- User login | G | Design |  | 2016-10-11 | 2016-10-11 |  | 2016-10-17 | 2016-10-17
--- Account maintenance | G | Design |  | 2016-10-11 | 2016-10-11 |  | 2016-10-17 | 2016-10-17
--- Catalog maintenance | G | Design |  | 2016-10-18 | 2016-10-18 |  | 2016-10-24 | 2016-10-24
--- Browse catalog | G | Design |  | 2016-10-25 | 2016-10-25 |  | 2016-10-31 | 2016-10-31
--- Add to shopping cart | G | Design |  | 2016-11-01 | 2016-11-01 |  | 2016-11-09 | 2016-11-09
etc. . .
Key Issues
Description |  | Status | Resolution/Update |  |  |  | Owner
Team member is on vaction |  | G | Darryl will be away on a camping trip until Sunday morning and will not have internet access. He will resume in helping with the project once he comes back |  |  |  | Darryl
Weekly group meetings |  | Y | The weekly one hour meetings between the team members are sometimes not enough. We suggested proposing a two meetings a week, however it is difficult to find a second convient time due to everyone's busy schedules. |  |  |  | Team
Planned Accomplishments
The team plans to have a draft of what will be included in the prototype so that it will be ready for disscusion by the next meeting. Hopefully after this meeting occurs, the team will have a clear idea of what should be included in the application so that we can get started right away in building a prototype.