## Status Summary
Project Dashboard
Note: Project plan with original dates and actual dates should be attached. | [6 empty] | Date: | 2016-09-29
Project Name: | Implement a Delivery System for Fresh Grocery Items | [5 empty] | Project Status: | Y
Project Description: | Millennial consumers are concerned about the long-term health effects of biotechnology and pesticides. They're looking at down-the-road diseases like cancer, heart disease, obesity and the "unknown." This project will create a direct selling platforms for fruit and vegetable to be delivered from farm to table and give the consumers confidence that safety precautions were taken prior to purchase.
Customer | Joe Smith, Manager, Customer Relations
Project Core Team: | Lamar Dixon, Darryl Jones, Nicholas Stamboolian, Ryan Trapp, and Celynna Zoleta
Next Milestone: | Construction of Prototype
Phase Status
| Status | Plan |  | Status | Plan |  | Status | Date
Analysis | Y | 2016-09-27 | Testing | R | 2016-11-17
Design | R | 2016-10-04 | Installation | R | 2016-12-06
Construction | R | 2016-10-20
Leading Indicators | Status |  |  | Status |  |  | Status
On-Time | Y | On-Budget |  | G | Delivery to Scope |  | Y
Major Accomplishments/Decisions
As a team, we have decided it is crucial to meet twice a week to discuss the progress of the project. We have sent out a doodle form to find exact times that would be best for all members to meet. These future meetings are very crucial because we are falling behind schedule due to more confusions over the project's overall goal. To fix this confusion, we have had each member do their own personal research about the farming industry, delivery methods, and anything else relvant to the project so that they may be ablke to contribute ideas in our future weekly meetings. Additionally, we have also established what each team members is responsible for (documentations, gathering data, protyping, etc.) and have given each member a list of tasks to be completed before hand.
CURRENT KEY ACTIVITIES --- NOTE ACTUAL (VS PROJECTED) DATES ARE INDICATED BY ITALICS
|  |  |  | START |  |  | END
Current Key Activities | STATUS |  | PHASE | PLAN | ACT | Comments | PLAN | ACT
Test plan | Y | Design |  | 2016-09-10 | 2016-09-13 | Project idea conflicts | 2016-09-20 | 2016-09-20
Final project plan | R | Analysis |  | 2016-09-21 | 2016-09-21 |  | 2016-09-27 | 2016-09-29
UI Mockup | Y | Design
--- User login | Y | Design |  | 2016-10-11 | 2016-10-11 |  | 2016-10-17 | 2016-10-17
--- Account maintenance | Y | Design |  | 2016-10-11 | 2016-10-11 |  | 2016-10-17 | 2016-10-17
--- Catalog maintenance | Y | Design |  | 2016-10-18 | 2016-10-18 |  | 2016-10-24 | 2016-10-24
--- Browse catalog | Y | Design |  | 2016-10-25 | 2016-10-25 |  | 2016-10-31 | 2016-10-31
--- Add to shopping cart | Y | Design |  | 2016-11-01 | 2016-11-01 |  | 2016-11-09 | 2016-11-09
etc. . .
Key Issues
Description |  | Status | Resolution/Update |  |  |  | Owner
Busy Schedules |  | R | The team was not able to meet twice a week as previously planned. This is mainly due to the fact team members have other priorities such as schoolwork and exams. Because of this, the project is facing delays and at risk of not completing everything on schedule |  |  |  | Team
Doodle Form |  | G | A doodle form was sent out this week to see the exact time when members are free. We will use these responses to schedule exact times for the two weekly meetings in order to keep with the project schedule |  |  |  | Team
Planned Accomplishments
We will have a working prototype within the next week. The earlier we start on the prototype, the more time the team will have to decide on what's missing, what doesn't belong, and what features we could possibily enchance.