## Status Summary
Project Dashboard
Note: Project plan with original dates and actual dates should be attached. | [6 empty] | Date: | 2016-10-20
Project Name: | Implement a Delivery System for Fresh Grocery Items | [5 empty] | Project Status: | G
Project Description: | Millennial consumers are concerned about the long-term health effects of biotechnology and pesticides. They're looking at down-the-road diseases like cancer, heart disease, obesity and the "unknown.” Farmers sell untouched items directly to consumers by having their items sold at farmer’s markets, however there are only a few available. There are more groceries stores in areas than there is farmer’s markets that it is hard for consumers to buy fresh products. This project will create an easy way to shop at farmer’s markets by creating an application that delivers items from farmers-to-consumers. This will give farmers’ more sales and may even attract a new market who has never shopped for fresh items.
Customer | Joe Smith, Manager, Customer Relations
Project Core Team: | Lamar Dixon, Darryl Jones, Nicholas Stamboolian, Ryan Trapp, and Celynna Zoleta
Next Milestone: | Construction of Prototype
Phase Status
| Status | Plan |  | Status | Plan |  | Status | Date
Analysis | G | 2016-09-27 | Testing | Y | 2016-11-17
Design | Y | 2016-10-04 | Installation | Y | 2016-12-06
Construction | Y | 2016-10-20
Leading Indicators | Status |  |  | Status |  |  | Status
On-Time | Y | On-Budget |  | G | Delivery to Scope |  | G
Major Accomplishments/Decisions
-The team was assigned an IBIT project mentor who will be able to help guide us in our project. Our mentor's name is Bruce Fadem who is a retired VP & CIO at Wyeth. Furthermore, Nick has started on creating a prototype while the rest of the team has drawn out ideas on what they want to be included in the application's interface. Lastly, the team now has a better understanding of our project and what our projects goal should meet. We have agreed to elimate the farmer to consumer idea and just have our drivers pick up order items from a local farmer's market. By doing this, we hope to lure in new consumers who have never shopped at a farmers market but would be open to the idea of it with our application.
CURRENT KEY ACTIVITIES --- NOTE ACTUAL (VS PROJECTED) DATES ARE INDICATED BY ITALICS
|  |  |  | START |  |  | END
Current Key Activities | STATUS |  | PHASE | PLAN | ACT | Comments | PLAN | ACT
Test plan | G | Design |  | 2016-09-10 | 2016-09-13 | Project idea conflicts | 2016-09-20 | 2016-09-20
Final project plan | G | Analysis |  | 2016-09-21 | 2016-09-21 |  | 2016-09-27 | 2016-09-29
UI Mockup | Y | Design
--- User login | Y | Design |  | 2016-10-11 | 2016-10-15 |  | 2016-10-17 | Processing
--- Account maintenance | Y | Design |  | 2016-10-11 | 2016-10-15 |  | 2016-10-17 | Processing
--- Catalog maintenance | Y | Design |  | 2016-10-27 |  |  | 2016-11-02
--- Browse catalog | Y | Design |  | 2016-10-27 |  |  | 2016-11-02
--- Add to shopping cart | Y | Design |  | 2016-11-03 |  |  | 2016-11-10
etc. . .
Key Issues
Description |  | Status | Resolution/Update |  |  |  | Owner
Confusing with pricing the application |  | G | We have decided to eliminate the idea of subscribtion fees. |  |  |  | Team
How to handle delivery time frame |  | Y | We need to decide how well delivery will meet customer satisfaction (i.e is same day delivery policy) |  |  |  | Team
Planned Accomplishments
We will continue to work on the prototype and present to the class for feedback during the second status report (10/20/2016). As a team, we will schedule a meet and greet with our appointed mentor.