## Status Summary
Project Dashboard
Note: Project plan with original dates and actual dates should be attached. | [6 empty] | Date: | 2016-11-10
Project Name: | InstaFresh | [5 empty] | Project Status: | Y
Project Description: | Millennial consumers are concerned about the long-term health effects of biotechnology and pesticides. They're looking at down-the-road diseases like cancer, heart disease, obesity and the "unknown.” Farmers sell untouched items directly to consumers by having their items sold at farmer’s markets, however there are only a few available. There are more groceries stores in areas than there is farmer’s markets that it is hard for consumers to buy fresh products. This project will create an easy way to shop at farmer’s markets by creating an application that delivers items from farmers-to-consumers. This will give farmers’ more sales and may even attract a new market who has never shopped for fresh items.
Customer | Joe Smith, Manager, Customer Relations
Project Core Team: | Lamar Dixon, Darryl Jones, Nicholas Stamboolian, Ryan Trapp, and Celynna Zoleta
Next Milestone: | Finishing Prototype and Documents
Phase Status
| Status | Plan |  | Status | Plan |  | Status | Date
Analysis | G | 2016-09-27 | Testing | Y | 2016-11-17
Design | G | 2016-10-04 | Installation | Y | 2016-12-06
Construction | Y | 2016-10-20
Leading Indicators | Status |  |  | Status |  |  | Status
On-Time | Y | On-Budget |  | G | Delivery to Scope |  | G
Major Accomplishments/Decisions
We made revisions to the project charter primarily focusing on rewording the project description and project scope sections. Additionally, we also made our overall work schedule and work breakdown structure more in depth to make each step within each phases more clearer. We also took advice from our mentor Bruce Fadem who said we should recreate our project plan, we we have successfully did and uploaded to our shared drive. From this project plan, we will have a better way to see what is due on specific dates and who is assigned these tasks. The team has also begain completing documents needed for the final presentation and have started building our team site.
CURRENT KEY ACTIVITIES --- NOTE ACTUAL (VS PROJECTED) DATES ARE INDICATED BY ITALICS
|  |  |  | START |  |  | END
Current Key Activities | STATUS |  | PHASE | PLAN | ACT | Comments | PLAN | ACT
Test plan | G | Design |  | 2016-09-10 | 2016-09-13 | Project idea conflicts | 2016-09-20 | 2016-09-20
Final project plan | G | Analysis |  | 2016-09-21 | 2016-09-21 |  | 2016-09-27 | 2016-09-29
UI Mockup | Y | Design
--- User login | Y | Design |  | 2016-10-11 | 2016-10-15 |  | 2016-10-17 | 2016-10-26
--- Account maintenance | Y | Design |  | 2016-10-11 | 2016-10-15 |  | 2016-10-17 | 2016-10-26
--- Catalog maintenance | Y | Design |  | 2016-10-27 | 2016-10-29 |  | 2016-11-02 | 2016-11-10
--- Browse catalog | Y | Design |  | 2016-10-27 | 2016-10-29 |  | 2016-11-02 | 2016-11-10
--- Add to shopping cart | Y | Design |  | 2016-11-03 | 2016-11-05 |  | 2016-11-10 | 2016-11-10
etc. . .
Key Issues
Description |  | Status | Resolution/Update |  |  |  | Owner
Prototype Delay |  | R | Too much focus on documentation rather than prototype. |  |  |  | Team
Team
Planned Accomplishments
Finished completed prototype within the next week along with final documentation for the final presentation.