## Status Summary
Project Dashboard
Note: Project plan with original dates and actual dates should be attached. | [6 empty] | Date: | 2016-11-10
Project Name: | InstaFresh | [5 empty] | Project Status: | Y
Project Description: | Millennial consumers are concerned about the long-term health effects of biotechnology and pesticides. They're looking at down-the-road diseases like cancer, heart disease, obesity and the "unknown.” Farmers sell untouched items directly to consumers by having their items sold at farmer’s markets, however there are only a few available. There are more groceries stores in areas than there is farmer’s markets that it is hard for consumers to buy fresh products. Additionally, it is very difficult for farmers to make sales, especially in the winter time.This project will create an easy way to shop at farmer’s markets by creating an application that delivers items from farmers-to-consumers. This will give farmers’ more sales and may even attract a new market who has never shopped for fresh items.
Customer | Joe Smith, Manager, Customer Relations
Project Core Team: | Lamar Dixon, Darryl Jones, Nicholas Stamboolian, Ryan Trapp, and Celynna Zoleta
Next Milestone: | Finalizing the Project
Phase Status
| Status | Plan |  | Status | Plan |  | Status | Date
Analysis | G | 2016-09-27 | Testing | Y | 2016-11-17
Design | G | 2016-10-04 | Installation | Y | 2016-12-06
Construction | Y | 2016-10-20
Leading Indicators | Status |  |  | Status |  |  | Status
On-Time | Y | On-Budget |  | G | Delivery to Scope |  | G
Major Accomplishments/Decisions
We met with our mentor Bruce for a second meeting and updated him on all our project deliverables. We recieved feedback on our financials and competitive analysis and took notes on what to needs to be edited and improved. Additionally, the project site is in the works still but it is almost close to completion. As for our prototype, we have built a functional working application, and all that needs to be finished is making the functionality of a shopping cart to work.
CURRENT KEY ACTIVITIES --- NOTE ACTUAL (VS PROJECTED) DATES ARE INDICATED BY ITALICS
|  |  |  | START |  |  | END
Current Key Activities | STATUS |  | PHASE | PLAN | ACT | Comments | PLAN | ACT
Test plan | G | Design |  | 2016-09-10 | 2016-09-13 | Project idea conflicts | 2016-09-20 | 2016-09-20
Final project plan | G | Analysis |  | 2016-09-21 | 2016-09-21 |  | 2016-09-27 | 2016-09-29
UI Mockup | Y | Design
--- User login | Y | Design |  | 2016-10-11 | 2016-10-15 |  | 2016-10-17 | 2016-10-26
--- Account maintenance | Y | Design |  | 2016-10-11 | 2016-10-15 |  | 2016-10-17 | 2016-10-26
--- Catalog maintenance | Y | Design |  | 2016-10-27 | 2016-10-29 |  | 2016-11-02 | 2016-11-10
--- Browse catalog | Y | Design |  | 2016-10-27 | 2016-10-29 |  | 2016-11-02 | 2016-11-10
--- Add to shopping cart | Y | Design |  | 2016-11-03 | 2016-11-05 |  | 2016-11-10 | 2016-11-10
etc. . .
Key Issues
Description |  | Status | Resolution/Update |  |  |  | Owner
Prototype |  | R | Needs a farmer's use case, which would be a new prototype. |  |  |  | Team
Final Presentation |  | Y | Deadline is coming up soon, with little time left to fix everything. |  |  |  | Team
Planned Accomplishments
Finish all required documentation over the Thanksgiving break so that we can focus on the final presentation.