## Sheet1
Project Dashboard
Note: Project plan with original dates and actual dates should be attached. | [6 empty] | Date: | 2015-02-12
Project Name: | Kick the Bucket | [5 empty] | Project Status: | Y
Project Description: | There is an opportunity in the Web 2.0 marketplace for an application that takes advantage of social networking technologies to connect people with similar life goals. Kick The Bucket will provide a platform for creating individual users’ life goal lists and matching users with similar lists, allowing them to collaborate on a plan to achieve there shared goals. The platform will include tools for time and resource management to assist users in completing their goals together.
Customer
Project Core Team: | James Brunetto, Anne Buckley, Angela Gilson, Andre Messa, and Matt Ortiz
Next Milestone: | Prototype
Phase Status
| Status | Plan |  | Status | Plan |  | Status | Date
Analysis | Y | 2015-01-20 | Testing | G | 2015-03-15
Design | G | 2015-02-15 | Installation | G | 2015-04-30
Construction | Y | 2015-02-20
Leading Indicators | Status |  |  | Status |  |  | Status
On-Time | Y | On-Budget |  | G | Delivery to Scope |  | G
Major Accomplishments/Decisions
Defined a clear objective for our project. Created Project Charter and Business Model.
CURRENT KEY ACTIVITIES --- NOTE ACTUAL (VS PROJECTED) DATES ARE INDICATED BY ITALICS
|  |  |  | START |  |  | END
Current Key Activities | STATUS |  | PHASE | PLAN | ACT | Comments | PLAN | ACT
Creation of project charter | G |  |  | 2015-02-01 | 2015-02-01 |  | 2015-02-15 | 2015-02-15
Creation of business model | G |  |  | 2015-12-01 | 2015-02-04 |  | 2015-02-04 | 2015-01-10
Business rules | G |  |  | 2015-02-01 | 2015-02-01
Scope document | G |  |  | 2015-02-01 | 2015-02-04
G
G
G
G
Key Issues
Description |  | Status | Resolution/Update |  |  |  | Owner
Customer execution |  | Y
Customer retention |  | Y
Customer acquisition |  | Y
Assurance of safety/building trust |  | Y
Planned Accomplishments
Establish reliable time slot for weekly group meetings. Begin work on prototype. Begin resolution of key issues.