## Status Summary
Project Dashboard
Note: Project plan with original dates and actual dates should be attached. | [6 empty] | Date: | 2015-11-10
Project Name: | Apraisal Application | [5 empty] | Project Status: | Y
Project Description: | An appraisal application that will lead to increased purchases for Legacy Collectibles.
Customer | Legacy Collectibles' customers. People with old militaria
Project Core Team: | Jeff, Kenny, Kurt
Next Milestone: | Completed Prototype
Phase Status
| Status | Plan |  | Status | Plan |  | Status | Date
Analysis | Y |  | Testing | Y
Design | Y |  | Installation | Y
Construction | Y
Leading Indicators | Status |  |  | Status |  |  | Status
On-Time | Y | On-Budget |  | G | Delivery to Scope |  | G
Major Accomplishments/Decisions
We completed the outline of our project and laid the foundation for design and functionality for our prototype. We also set up our project website and have begun to add to it to report progress of our project. We decided Kenny would be the laison for our mentor. We scheduled to meet with our mentor next week.
CURRENT KEY ACTIVITIES --- NOTE ACTUAL (VS PROJECTED) DATES ARE INDICATED BY ITALICS
|  |  |  | START |  |  | END
Current Key Activities | STATUS |  | PHASE | PLAN | ACT | Comments | PLAN | ACT
Test plan | G | Design |  |  |  | Created Sketches | 2015-10-27 | 2015-10-27
Final project plan | Y | Analysis |  | 2015-10-15 | 2015-10-27 | Scope issues | 2015-10-25 | 2015-10-26
UI Creation | G | Design |  |  | 2015-10-30 |  | 2015-11-05
--- Landing Page | G | Design |  | 2015-10-31 | 2015-10-30 |  | 2015-11-06
--- Stem/Branch Pages | Y | Design |  | 2015-10-31 | 2015-10-31 | Not all pages complete | 2015-11-07 | 2015-11-13
--- Database maintenance | R | Design |  | 2015-10-31 | 2015-11-01 |  | 2015-11-08 | 2015-11-15
--- Email to Legacy Collectibles | R | Design |  | 2015-10-31 | 2015-11-02 |  | 2015-11-15
--- Completing Purchase Process | Y | Design |  | 2015-10-31 | 2015-11-03 |  | 2015-11-15
Test Prototype | Y | Analysis |  |  | 2015-11-10 |  | 2015-11-21
Key Issues
Description |  | Status | Resolution/Update |  |  |  | Owner
Not a big enough database |  | Y | We can manually enter our expertise into the evaluation formula (ex: serial number ranges). |  |  |  | Kurt
Customers not Adopting new App. |  | Y | User-friendly interface. |  |  |  | Client
Inaccurate appraisals |  | Y | Give a lower-end estimate |  |  |  | Group
Creating Email notifications to Legacy |  | R | We need to figure out how Legacy will be notified |  |  |  | Kurt
Integration with databases |  | R | How will this integrate and check/scan databases? |  |  |  | Jeff
Planned Accomplishments
Next week we plan to meet with our mentor, and receive feedback on our progress. We plan to complete the prototype as well, and make progress on our key database issues.
Note on B46: Key Issues are issues that need your CM Director-level understanding and awareness.