## Status Summary
Project Dashboard
Note: Project plan with original dates and actual dates should be attached. | [6 empty] | Date: | 2015-11-17
Project Name: | Apraisal Application | [5 empty] | Project Status: | Y
Project Description: | Legacy Collectibles is a small business that buys and sells military collectibles online. Every week they receive offers from individuals who are selling militaria and would like an appraisal. We created an appraisal website that will act as a sister site to Legacy Collectibles that will lead to expedited and increased purchases for the company.
Customer | Legacy Collectibles' customers. People with old militaria
Project Core Team: | Jeff, Kenny, Kurt
Next Milestone: | Completed and Presentable Prototype
Phase Status
| Status | Plan |  | Status | Plan |  | Status | Date
Analysis | G |  | Testing | Y
Design | G |  | Installation | R
Construction | Y
Leading Indicators | Status |  |  | Status |  |  | Status
On-Time | Y | On-Budget |  | G | Delivery to Scope |  | G
Major Accomplishments/Decisions
This week we met with our mentor. He gave us great feedback on how to present and describe our project. We no longer refer to this as an application, but instead a sister-site to Legacy Collectibles. Based on feedback we received in class, we have modified the way our website works to make the appraisal process even more user-friendly. We have also kept our project website up to date. We scheduled to meet with our mentor next week, as well as our Project Champion/Professor.
CURRENT KEY ACTIVITIES --- NOTE ACTUAL (VS PROJECTED) DATES ARE INDICATED BY ITALICS
|  |  |  | START |  |  | END
Current Key Activities | STATUS |  | PHASE | PLAN | ACT | Comments | PLAN | ACT
Test plan | G | Design |  |  |  | Created Sketches | 2015-10-27 | 2015-10-27
Final project plan | G | Analysis |  | 2015-10-15 | 2015-10-27 | Scope issues | 2015-10-25 | 2015-10-26
UI Creation | G | Design |  |  | 2015-10-30 |  | 2015-11-05
--- Landing Page | G | Design |  | 2015-10-31 | 2015-10-30 |  | 2015-11-06
--- Stem/Branch Pages | Y | Design |  | 2015-10-31 | 2015-10-31 | Not all pages complete | 2015-11-07 | 2015-11-13
--- Database maintenance | Y | Design |  | 2015-10-31 | 2015-11-01 |  | 2015-11-08 | 2015-11-15
--- Email to Legacy Collectibles | R | Design |  | 2015-10-31 | 2015-11-02 |  | 2015-11-15
--- Completing Purchase Process | G | Design |  | 2015-10-31 | 2015-11-03 |  | 2015-11-15
Test Prototype | Y | Analysis |  |  | 2015-11-10 |  | 2015-11-21
Key Issues
Description |  | Status | Resolution/Update |  |  |  | Owner
Not a big enough database |  | G | We can manually enter our expertise into the evaluation formula (ex: serial number ranges). |  |  |  | Kurt
Customers not Adopting new App. |  | G | User-friendly interface. |  |  |  | Client
Inaccurate appraisals |  | G | Give a lower-end estimate - higher Legacy margin. |  |  |  | Group
Creating Email notifications to Legacy |  | R | We need to figure out how Legacy will be notified |  |  |  | Kurt
Integration with databases |  | Y | How will this integrate and check/scan databases? |  |  |  | Jeff
Planned Accomplishments
Next week we will finish the modifications to our website prototype. We will also meet with our Professor and Mentor and give our "mock presentation". We also plan to address the back-end of the prototype, as far as an email notification every time an appraisal is made.
Note on B46: Key Issues are issues that need your CM Director-level understanding and awareness.