## Status Summary
Project Dashboard
[7 empty] | Date: | 2015-11-24
Project Name: | Apraisal Application | [5 empty] | Project Status: | G
Project Description: | Legacy Collectibles is a small business that buys and sells military collectibles online. Every week they receive offers from individuals who are selling militaria and would like an appraisal. We created an appraisal website that will act as a sister site to Legacy Collectibles that will lead to expedited and increased purchases for the company.
Customer | Legacy Collectibles' customers. People with old militaria
Project Core Team: | Jeff, Kenny, Kurt
Next Milestone: | Completed and Presentable Prototype
Phase Status
| Status | Plan |  | Status | Plan |  | Status | Date
Analysis | G |  | Testing | G
Design | G |  | Installation | Y
Construction | Y
Leading Indicators | Status |  |  | Status |  |  | Status
On-Time | G | On-Budget |  | G | Delivery to Scope |  | G
Major Accomplishments/Decisions
This week we had our second meeting with the mentor. He approved our changes to the charter and liked our new approach to the project/website. We finalized and clarified the changes in layout for our website to make the process much more user friendly. We have made the appropriate changes to our project website as well. We also discussed and determined how we would pull values from the Legacy-Collectibles database. We scheduled to meet with our mentor next week (Monday 11am), and we have a meeting with the professor at 8am on Saturday.
CURRENT KEY ACTIVITIES --- NOTE ACTUAL (VS PROJECTED) DATES ARE INDICATED BY ITALICS
|  |  |  | START |  |  | END
Current Key Activities | STATUS |  | PHASE | PLAN | ACT | Comments | PLAN | ACT
Test plan | G | Design |  |  |  | Created Sketches | 2015-10-27 | 2015-10-27
Final project plan | G | Analysis |  | 2015-10-15 | 2015-10-27 | Scope issues | 2015-10-25 | 2015-10-26
UI Creation | G | Design |  |  | 2015-10-30 |  | 2015-11-05
--- Landing Page | G | Design |  | 2015-10-31 | 2015-10-30 |  | 2015-11-06
--- Stem/Branch Pages | G | Design |  | 2015-10-31 | 2015-10-31 | Not all pages complete | 2015-11-07 | 2015-11-13
--- Database maintenance | G | Design |  | 2015-10-31 | 2015-11-01 |  | 2015-11-08 | 2015-11-15
--- Email to Legacy Collectibles | Y | Design |  | 2015-10-31 | 2015-11-02 |  | 2015-11-15
--- Completing Purchase Process | G | Design |  | 2015-10-31 | 2015-11-03 |  | 2015-11-15
Test Prototype | Y | Analysis |  |  | 2015-11-10 |  | 2015-11-21
Key Issues
Description |  | Status | Resolution/Update |  |  |  | Owner
Not a big enough database |  | G | We can manually enter our expertise into the evaluation formula (ex: serial number ranges). |  |  |  | Kurt
Customers not Adopting new App. |  | G | User-friendly interface. |  |  |  | Client
Inaccurate appraisals |  | G | Give a lower-end estimate - higher Legacy margin. |  |  |  | Group
Creating Email notifications to Legacy |  | Y | We need to figure out how Legacy will be notified |  |  |  | Kurt
Integration with databases |  | Y | How will this integrate and check/scan databases? |  |  |  | Jeff
ASSUMPTIONS |  | G
Planned Accomplishments
Next week we will finalize and smooth out any issues with the prototype and presentation. We will create the slide deck for our powerpoint presentation as supplement to the prototype. We will also meet with our Professor and Mentor and give our "mock presentation" in final preperation for project completion.
Note on B46: Key Issues are issues that need your CM Director-level understanding and awareness.