## Status Summary
Project Dashboard
[7 empty] | Date: | 2018-09-13
Project Name: | LimitList | [5 empty] | Project Status: | Y
Project Description: | Create a scalable app that allows small supermarket owners to explore online delivery and compete with larger grocery store chains as well as provide dashboard that optimizes delivery for in-store shoppers.
Customer | Small Supermarkets and Shoppers
Project Core Team: | Anna Davitashvili, Ahmad Ibrahim, Chung Han Tu
Next Milestone: | Analyze and brainstorm - Process model, data model, system architechture diagram
Phase Status
| Status | Plan |  | Status | Plan |  | Status | Date
Proposal | G | 2018-09-06 | Dress rehersal | Y | 2018-11-27
Design | Y | 2018-10-02 | Showcase | Y | 2018-12-04
Prototype | Y | 2018-10-23
Leading Indicators | Status |  |  | Status |  |  | Status
On-Time | Y | On-Budget |  | Y | Delivery to Scope |  | Y
Major Accomplishments/Decisions
Last week we created an intial proposal for our project.
CURRENT KEY ACTIVITIES --- NOTE ACTUAL (VS PROJECTED) DATES ARE INDICATED BY ITALICS
|  |  |  | START |  |  | END
Current Key Activities | STATUS |  | PHASE | PLAN | ACT | Comments | PLAN | ACT
Process Model | Y | Design |  | 2018-09-13 |  |  | 2018-10-10
Data Model | Y | Design |  | 2018-09-13 |  |  | 2018-10-10
System Architechture Diagram | Y | Design |  | 2018-09-13 |  |  | 2018-10-10
Key Issues
Description |  | Status | Resolution/Update |  |  |  | Owner
Planned Accomplishments
This week we will begin planning our models so that we have a blue print for prototype.
Note on B46: Key Issues are issues that need your CM Director-level understanding and awareness.