## Stakeholder example
Stakeholder Name/Title | Stakehold Project Role | Responsibilities | Interest | Success Criteria | Concerns | Technical Proficiency/Work Environment Constraints
NA General Manager | Project Sponsor | Over sees wharehouse operation | Save money and increase customer satisfaction | lower number of rush orders and increase flow of items out of the warehouse | Lost revenue and customer base
Customer Service | SME | Takes orders | Satisfy customers, | spend less time placing rush orders | Do not want a new order system | no changes to order system
Customer | SME | Place orders | Process is time consuming | Quick order delivery | no back orders
Plants | SME | Manufactore product | Smoother operations | Less rush orders | interruption of productoin for rush orders
Warehouse | SME | Store products | Faster Forklifts | All items on invioce are in the warehouse | Items get placed in the wrong location | too much automation
Customer Service Rep | SME | Respond to customer request
Shipping team | SME | Pick list and selection in warehouse | Prepares orders In the warehouse | reducding in manaual paper work
Warehouse Personel | SME | maintain inventory in warehouse | Manges inventory in the warehouse
Carriers | SME |  | Delivers product | reduced loading time
PM | Project Team | Organize Project tasks, communications and Reporting | Successful Project delivery | Satified project sponsor | Contract resouce with little knowledge of the organizations culture
Business Analyst | Project Team | Document AS and To be states | Identify solution | Satified project sponsor
Order system | IT DBA / Architect | Technology support
Inventory System | IT DBA / Architect | Technology support

## Core Business Requirements
Core Requirements Identification Template
Process / Use cases | External Agents / Actors | Data - Entities and Attributes | Business Rules
Take orders Check invintory | Customer Service Rep Customer | Products and Product attributes Inventory | Availablity rules
Cancel Order | Customer Rep Customer Service | Inventory | Can not meet the agreed delivery date
Rush orders | Customer Service General Manager Carrier Warehouse Shipping | Master Production Schedule Distribution System | Pending order with no inventory
Creates Pick list Create Shipping papers | Shipping team | Distribution System Inventory
Intake inventory to warehose | Warehouse personnel | Inventory | Where to place intake
Orders Picked and loaded | Warehouse personnel | Shipping Order Tracking | If items not found
Dispatching | Carriers | Distribution System | What carrier