## Status Summary
Project Dashboard
Note: Project plan with original dates and actual dates should be attached. | [6 empty] | Date: | 2017-10-16
Project Name: | Community Platform Analytics | [5 empty] | Project Status: | Y
Project Description: | The MIS program at the Fox School of Business at Temple University is one of the biggest and rigorous programs at the university. As a top 15th ranked program of its type in the country, the MIS has utilized a points system in order to professionally develop their students and prepare them for their career. However, each year students run into issues of not being able to register for classes due to their lack of MIS points. Inability to earn credit for classes or not being able to progress in the MIS curriculum may result in students not being able to graduate on time. There is currently no single solution that integrates the student’s background and current point status to inform these student about opportunities to earn points. To effectively address the issue, our solution will analyze students data, find patterns, and provide a solution to help students stay on track in the MIS curriculum and professional development.
Customer | Temple University MIS Department
Project Core Team: | Marc Gold: Documentation and Communications to MIS Dept. Adriana Shuster: Prototype Design Josh Veloso: Project Manager Run Zhu: Analytics & Prototyping
Next Milestone: | Delivery of Cleaned Data Set
Phase Status
| Status | Plan |  | Status | Plan |  | Status | Date
Analysis | Y | 2017-10-15 | Testing | G | 2017-12-01 |  | Y | 2017-10-16
Design | G | 2017-11-01 | Installation | G | 2017-12-10
Construction | G | 2017-11-15
Leading Indicators | Status |  |  | Status |  |  | Status
On-Time | Y | On-Budget |  | G | Delivery to Scope |  | Y
Major Accomplishments/Decisions
1. Assigned Group Project Mentor
CURRENT KEY ACTIVITIES --- NOTE ACTUAL (VS PROJECTED) DATES ARE INDICATED BY ITALICS
|  |  |  | START |  |  | END
Current Key Activities | STATUS |  | PHASE | PLAN | ACT | Comments | PLAN | ACT
Obtain Data | G | Analysis |  | 2017-09-21 | 2017-09-24 |  | 2017-09-28 | 2017-09-28
Data Cleaning | Y | Analysis |  | 2017-10-01 | 2017-10-02 | Need follow-up with Munir | 2017-10-10
Data Categorization | Y | Analysis |  | 2017-10-10 |  |  | 2017-10-15
Data Analysis | Y | Analysis |  | 2017-10-15 |  |  | 2017-11-01
Research | G | Analysis |  | 2017-09-21 | 2017-09-21 |  | 2017-10-10
Key Issues
Description |  | Status | Resolution/Update |  |  |  | Owner
Dirty Data |  | Y | The dirty sets we have obtain have many null values and blanks |  |  |  | Munir Mandviwalla
Unable to find consistent meeting time |  | Y | The group will meet with our mentor for the first time as a team |  |  |  | Team
Planned Accomplishments
We were not able to meet with our mentor, so this week we are meeting with Munir to discuss the data sets that he provided us. After the meeting, we hope to have a clear direction on the analysis of the data set. Once we have a clear understanding of the data, we can properly prepare the data for analysis.
Note on B46: Key Issues are issues that need your CM Director-level understanding and awareness.