## Status Summary
Project Dashboard
Note: Project plan with original dates and actual dates should be attached. | [6 empty] | Date: | 2016-03-22
Project Name: | Freshly Picked App | [5 empty] | Project Status: | R
Project Description: | Freshly Picked App – Uses existing product SKU’s to collect and maintain product and transactional data, create reports, and provide value added decisions to end users through predictive analytics.
Customer | Everyday user, Commercial business , FDA (Government)
Project Core Team: | Anthony DeMaio, Paul Carbone, Frank Lo, Christopher Edmundowicz
Next Milestone:
Phase Status
| Status | Plan |  | Status | Plan |  | Status | Date
Analysis | Y | 2016-02-09 | Testing | G | 2016-04-05
Design | G | 2016-02-16 | Installation | G | 2016-04-20
Construction | G | 2016-03-08
Leading Indicators | Status |  |  | Status |  |  | Status
On-Time | R | On-Budget |  | R | Delivery to Scope |  | Y
Major Accomplishments/Decisions
Just in Mind prototype tool finally working. Team able to start prototyping with design concepts in mind. Created front page, login page, error page, etc. Team project application is currently working, but still needs the data masters to populate tables.
CURRENT KEY ACTIVITIES --- NOTE ACTUAL (VS PROJECTED) DATES ARE INDICATED BY ITALICS
|  |  |  | START |  |  | END
Current Key Activities | STATUS |  | PHASE | PLAN | ACT | Comments | PLAN | ACT
Project proposal | G | Analysis |  | 2016-01-26 | 2016-01-26
Project charter | G | Analysis |  | 2016-02-02 | 2016-02-02
Project site and revised charter | G | Design/Analysis |  | 2016-02-09 | 2016-02-09
Prototype | G | Design |  | 2016-03-08 | TBA | Issue fixed | 2016-03-08 | 2016-03-22
First progress grade from mentor | R | Analysis |  | 2016-03-15 | TBA | Class change | 2016-03-22 | 2016-04-19
Revised charter, prototype, and site | Y | Design/Analysis |  | 2016-04-05
Team project presentations | Y | Implementation |  | 2016-04-12
MIS Project Showcase | Y | Presentation |  | 2016-04-19
Key Issues
Description |  | Status | Resolution/Update |  |  |  | Owner
Change in App idea |  | R | Team building to update new idea |  |  |  | Project Team
New deliverables due |  | R | Upload info by Thursday deadline |  |  |  | Anthony/Paul
Documents |  | G | Project documentation up to date |  |  |  | Anthony/Paul
Prototype |  | R | Just In Mind tool not working |  |  |  | Chris/Frank
Mentor |  | R | No mentor |  |  |  | Project Team
Planned Accomplishments
Finalize create rough draft of prototype for next class. Have all documentation complete. Start working on final phases of project for implementation.
Note on B46: Key Issues are issues that need your CM Director-level understanding and awareness.