## Status Summary
Project Dashboard
Note: Project plan with original dates and actual dates should be attached. | [6 empty] | Date: | 2016-03-08
Project Name: | Fresh-Code App | [5 empty] | Project Status: | R
Project Description: | Fresh-Code App – Uses existing product SKU’s to collect and maintain product and transactional data, create reports, and provide value added decisions to end users through predictive analytics.
Customer | Everyday user, Commercial business , FDA (Government)
Project Core Team: | Anthony DeMaio, Paul Carbone, Frank Lo, Christopher Edmundowicz
Next Milestone:
Phase Status
| Status | Plan |  | Status | Plan |  | Status | Date
Analysis | Y | 2016-02-09 | Testing | R | 2016-04-05
Design | R | 2016-02-16 | Installation | R | 2016-04-20
Construction | R | 2016-03-08
Leading Indicators | Status |  |  | Status |  |  | Status
On-Time | R | On-Budget |  | R | Delivery to Scope |  | Y
Major Accomplishments/Decisions
Working with Just in Mind customer service to get prototyping tool working on all team members’ computers. Designed a platform and mapped out entire architecture of Fresh Code application. Gained cooperation with group members on tasks and assignments.
CURRENT KEY ACTIVITIES --- NOTE ACTUAL (VS PROJECTED) DATES ARE INDICATED BY ITALICS
|  |  |  | START |  |  | END
Current Key Activities | STATUS |  | PHASE | PLAN | ACT | Comments | PLAN | ACT
Project proposal | G | Analysis |  | 2016-01-26 | 2016-01-26
Project charter | G | Analysis |  | 2016-02-02 | 2016-02-02
Project site and revised charter | G | Design/Analysis |  | 2016-02-09 | 2016-02-09
Prototype | R | Design |  | 2016-03-08 | TBA
First progress grade from mentor | R | Analysis |  | 2016-03-15 | TBA
Revised charter, prototype, and site | Y | Design/Analysis |  | 2016-04-05
Team project presentations | Y | Implementation |  | 2016-04-12
MIS Project Showcase | Y | Presentation |  | 2016-04-19
Key Issues
Description |  | Status | Resolution/Update |  |  |  | Owner
Change in App idea |  | R | Team building to update new idea |  |  |  | Project Team
New deliverables due |  | R | Upload info by Thursday deadline |  |  |  | Anthony/Paul
Documents |  | G | Project documentation up to date |  |  |  | Anthony/Paul
Prototype |  | R | Just In Mind tool not working |  |  |  | Chris/Frank
Mentor |  | R | No assigned mentor for project team |  |  |  | Project Team
Planned Accomplishments
Obtain working prototype tool. Gather further information on team mentor. Continue to work on updating documentation. Organize all team documentation and design back end into central location.
Note on B46: Key Issues are issues that need your CM Director-level understanding and awareness.