## Status Summary
Project Dashboard
Note: Project plan with original dates and actual dates should be attached. | [6 empty] | Date: | 2016-04-11
Project Name: | FreshlyPicked App | [5 empty] | Project Status: | G
Project Description: | • In the US, Americans throw away approximately $165 billion worth of food each year. • The average American household throws away up to $2,200 worth of food each year. Not many people can afford to throw $2,200 away every year, and Americans need to be more conscientious about expiration dates, wasting food, and spending habits at the grocery store because that amount could severely impact a family’s financial stability. By putting more thought and consideration into food expenditures, better decision making, and increased awareness of the shelf life of the food you already purchased, a household will have roughly an additional $100 per month for miscellaneous expenses.
Customer | Users that manage grocery shopping for households, everyday user, commercial business (i.e. grocery stores)
Project Core Team: | Anthony DeMaio, Paul Carbone, Frank Lo, Christopher Edmundowicz
Next Milestone: | Final Presentation of Application and Project Documentation
Phase Status
| Status | Plan |  | Status | Plan |  | Status | Date
Analysis | G | 2016-02-09 | Testing | G | 2016-04-05
Design | G | 2016-02-16 | Installation | G | 2016-04-20
Construction | G | 2016-03-08
Leading Indicators | Status |  |  | Status |  |  | Status
On-Time | G | On-Budget |  | G | Delivery to Scope |  | G
Major Accomplishments/Decisions
The biggest accomplishment was getting our team together to finalize the application and collectively work together to articulate the purpose, functionality, and value proposition in our project related documents.
CURRENT KEY ACTIVITIES --- NOTE ACTUAL (VS PROJECTED) DATES ARE INDICATED BY ITALICS
|  |  |  | START |  |  | END
Current Key Activities | STATUS |  | PHASE | PLAN | ACT | Comments | PLAN | ACT
Project proposal | G | Analysis |  | 2016-01-26 | 2016-01-26
Project charter | G | Analysis |  | 2016-02-02 | 2016-02-02
Project site and revised charter | G | Design/Analysis |  | 2016-02-09 | 2016-02-09
Prototype | G | Design |  | 2016-03-08 | TBA
First progress grade from mentor | G | Analysis |  | 2016-03-15 | TBA
Revised charter, prototype, and site | G | Design/Analysis |  | 2016-04-05 | 2016-04-18
Team project presentations | G | Implementation |  | 2016-04-12 | 2016-04-19 | Leading up to final activities, we will be rehearsing our presentation to ensure we communicate key information in the time allotted for the presentation
MIS Project Showcase | G | Presentation |  | 2016-04-19 | 2016-04-19
Key Issues
Description |  | Status | Resolution/Update |  |  |  | Owner
Change in App idea |  | R | Team building to update new idea |  |  |  | Project Team
New deliverables due |  | R | Upload info by Thursday deadline |  |  |  | Anthony/Paul
Documents |  | G | Project documentation up to date |  |  |  | Anthony/Paul
Prototype |  | G | Just In Mind tool not working |  |  |  | Chris/Frank
Mentor |  | R | No assigned mentor for project team |  |  |  | Project Team
Presentation Duration |  | G | Struggled to stay within time allotted for presentation, but after several rehersals that we recorded via video, we were able to identify what information we could eliminate to effectively deliver our presentation within the time restraints. |  |  |  | Project Team
Planned Accomplishments
Our team has achieved all of our goals that we had previously set, except for presentation execution. However, we are confident that after our presentation, we will be able to check off our presentation execution as a planned accomplishment that was successfully completed.
Note on B46: Key Issues are issues that need your CM Director-level understanding and awareness.