## Status Summary
Project Dashboard
Note: Project plan with original dates and actual dates should be attached. | [6 empty] | Date: | 2016-04-05
Project Name: | Freshly Picked App | [5 empty] | Project Status: | G
Project Description: | Freshly Picked App – Uses existing product SKU’s to collect and maintain product and transactional data, create reports, and provide value added decisions to end users through predictive analytics.
Customer | Everyday user, Commercial business , FDA (Government)
Project Core Team: | Anthony DeMaio, Paul Carbone, Frank Lo, Christopher Edmundowicz
Next Milestone: | Project Showcase
Phase Status
| Status | Plan |  | Status | Plan |  | Status | Date
Analysis | G | 2016-02-09 | Testing | G | 2016-04-05
Design | G | 2016-02-16 | Installation | G | 2016-04-20
Construction | G | 2016-03-08
Leading Indicators | Status |  |  | Status |  |  | Status
On-Time | G | On-Budget |  | Y | Delivery to Scope |  | Y
Major Accomplishments/Decisions
The biggest accomplishment was getting our project on track for success. All prototyping tools work and the project is in full development.
CURRENT KEY ACTIVITIES --- NOTE ACTUAL (VS PROJECTED) DATES ARE INDICATED BY ITALICS
|  |  |  | START |  |  | END
Current Key Activities | STATUS |  | PHASE | PLAN | ACT | Comments | PLAN | ACT
Project proposal | G | Analysis |  | 2016-01-26 | 2016-01-26
Project charter | G | Analysis |  | 2016-02-02 | 2016-02-02
Project site and revised charter | G | Design/Analysis |  | 2016-02-09 | 2016-02-09
Prototype | G | Design |  | 2016-03-08 | TBA
First progress grade from mentor | G | Analysis |  | 2016-03-15 | TBA
Revised charter, prototype, and site | G | Design/Analysis |  | 2016-04-05
Team project presentations | Y | Implementation |  | 2016-04-12
MIS Project Showcase | Y | Presentation |  | 2016-04-19
Key Issues
Description |  | Status | Resolution/Update |  |  |  | Owner
Change in App idea |  | R | Team building to update new idea |  |  |  | Project Team
New deliverables due |  | R | Upload info by Thursday deadline |  |  |  | Anthony/Paul
Documents |  | G | Project documentation up to date |  |  |  | Anthony/Paul
Prototype |  | G | Just In Mind tool not working |  |  |  | Chris/Frank
Mentor |  | R | No assigned mentor for project team |  |  |  | Project Team
Planned Accomplishments
Finish prototype, complete all documentation, and prepare for final presentation.
Note on B46: Key Issues are issues that need your CM Director-level understanding and awareness.