## Sheet1
Project Dashboard
Note: Project plan with original dates and actual dates should be attached. | [6 empty] | Date: | 2015-02-10
Project Name: | Parking App |  |  |  |  | Project Status: |  | Y
Project Description: | Build a crowdsourced parking mobile application that relies on updates from the user community to provide other users with information regarding available parking spots within a nearby location. This application will offer any community a way to easily cycle spots in order to provide more availability for customers.
Customer | People searching for parking in the city
Project Core Team: | Zack Bambary, Dan Kovacs, Bakari Malik, Tyler Sliney, Andrew Crerand
Next Milestone: | Defining requirements, Prototyping
Phase Status
| Status | Plan |  | Status | Plan |  | Status | Date
Research | G | 2015-01-20 | Design
Documentation | Y |  | Development
Requirements | Y |  | Final Presentation
Leading Indicators | Status |  |  | Status |  |  | Status
On-Time | Y | On-Budget |  | G | Delivery to Scope
Will determine status after more progress is made
Major Accomplishments/Decisions
After a few brainstorming sessions, we decided on our project plan and began creating a project charter. We are still waiting for approval on our project plan.
CURRENT KEY ACTIVITIES --- NOTE ACTUAL (VS PROJECTED) DATES ARE INDICATED BY ITALICS
|  |  | START |  |  | END
Current Key Activities | STATUS | PHASE |  | PLAN | ACT | Comments | PLAN | ACT
Determining demographic & what consumers this applies to | G | Research |  | 2015-01-20 | 2015-01-20 | Determined target market for Parking app. Looked for potential competition | 2015-01-31 | 2015-02-10
Develop Use Case | Y | Requirements |  | 2015-01-31 | 2015-02-09 |  | 2015-02-17
Develop Business Rules | Y | Requirements |  | 2015-02-09 |  |  | 2015-02-17
Start Prototype | Y | Design |  | 2015-02-17
Key Issues
Description |  | Status | Resolution/Update |  |  |  | Owner
Getting caught up with documentation |  | Y | Will be finalized by next class meeting (2/17/15) |  |  |  | Group
Planned Accomplishments
Our next step is to get remaining documentation and design completed so we can start protoyping.