## Status Summary
Project Dashboard
Note: Project plan with original dates and actual dates should be attached. | [6 empty] | Date:
Project Name: | ABC Project | [5 empty] | Project Status: | Y
Project Description: | Info from project charter
Customer | Joe Smith, Manager, Customer Relations
Project Core Team: | Team member names
Next Milestone: | Delivery of Testing plan
Phase Status
| Status | Plan |  | Status | Plan |  | Status | Date
Analysis | Y | 2003-12-31 | Testing | G | 2004-05-15
Design | G | 2004-02-15 | Installation | G | 2004-05-30
Construction | Y | 2004-04-30
Leading Indicators | Status |  |  | Status |  |  | Status
On-Time | Y | On-Budget |  | G | Delivery to Scope |  | G
Major Accomplishments/Decisions
Last week at a customer meeting, the customer approved our project plan. They disagreed with us, however with some things we thought were out of scope which they consider in scope. We are in the process of negotiating these issues now and will know if there will be any impact to the schedule.
CURRENT KEY ACTIVITIES --- NOTE ACTUAL (VS PROJECTED) DATES ARE INDICATED BY ITALICS
|  |  |  | START |  |  | END
Current Key Activities | STATUS |  | PHASE | PLAN | ACT | Comments | PLAN | ACT
Test plan | G | Design |  | 2005-02-01 | 2005-02-01 |  | 2005-02-15 | 2005-02-15
Final project plan | Y | Analysis |  | 2005-12-01 | 2005-12-01 | Scope issues | 2005-12-15 | 2005-01-10
UI Mockup | G | Design
--- User login | G | Design |  | 2005-01-15 | 2005-01-20 |  | 2005-01-22 | 2005-01-22
--- Account maintenance | G | Design |  | 2005-01-20 | 2005-01-20 |  | 2005-01-22 | 2005-01-24
--- Catalog maintenance | G | Design |  | 2005-02-01 | 2005-02-01 |  | 2005-02-03 | 2005-02-03
--- Browse catalog | G | Design |  | 2005-02-01 | 2005-02-01 |  | 2005-02-05 | 2005-02-05
--- Add to shopping cart | G | Design |  | 2005-02-04 | 2005-02-04 |  | 2005-02-06 | 2005-02-06
etc. . .
Key Issues
Description |  | Status | Resolution/Update |  |  |  | Owner
Access programmer on vacation |  | G | Monica is out until next week but she can catch up when she returns |  |  |  | Monica
Client trying to make changes |  | R | Client owes us updated changes by this Friday |  |  |  | Client
Planned Accomplishments
Next week we are meeting with the client to cover any scope changes they request. We also plan to deliver a draft of the mock-ups for them to review. When that is approved we can begin the UI design.
Note on B46: Key Issues are issues that need your CM Director-level understanding and awareness.