## Status Summary
Project Dashboard
Note: Project plan with original dates and actual dates should be attached. | [6 empty] | Date: | 2018-09-12
Project Name: | TryVitris Capstone Project | [5 empty] | Project Status: | R
Project Description: | Vitris clients need to consolidate and simplify customer interactions by implementing a member platform for sales, billing, customer service and field service requests. Currently, Vitris clients communicate with customers using email and web forms. Customers must re-enter their contact information each time they visit a client’s site. Additionally, Vitris clients must forward the customer request to the appropriate department prior to handling. By providing clients with a member platform, their customers can perform a variety self-service tasks, as well as gain greater insight into their purchases and client communication. Customers will be able to enter their own information into the CRM databases, reducing Vitris clients’ administrative workload. This new feature will expand Vitris’ current product offering, enabling them to deepen the relationships they have with existing clients.
Customer | Jack Perotta, President CEO of Vitris
Project Core Team: | Chandni Antala, Ariana Castaneda, Sarita Cini, Fatimata Sall
Next Milestone: | Creating the Process model, Data model, and System architecture diagram.
Phase Status
| Status | Plan |  | Status | Plan |  | Status | Date
Analysis | Y | 2018-10-02 | Testing | R | 2018-11-13
Design | R | 2018-10-23 | Installation | R | 2018-12-04
Construction | R | 2018-11-06
Leading Indicators | Status |  |  | Status |  |  | Status
On-Time | G | On-Budget |  | G | Delivery to Scope |  | Y
Major Accomplishments/Decisions
We now have a project to work on and completed the project charter.
CURRENT KEY ACTIVITIES --- NOTE ACTUAL (VS PROJECTED) DATES ARE INDICATED BY ITALICS
|  |  |  | START |  |  | END
Current Key Activities | STATUS |  | PHASE | PLAN | ACT | Comments | PLAN | ACT
Project Charter | Y | Analysis |  | 2018-09-06 | 2018-09-12 |  | 2018-09-13 | 2018-09-13
Project Deck | Y | Analysis |  | 2018-09-06 | 2018-09-13 |  | 2018-09-13 | 2018-09-13
Process Model | R | Analysis |  | 2018-09-14 |  |  | 2018-09-27
Data Model | R | Analysis |  | 2018-09-14 |  |  | 2018-09-27
System Architecture Design | R | Analysis |  | 2018-09-14 |  |  | 2018-09-27
Progress Report | R | Analysis |  | 2018-09-14 |  |  | 2018-09-27
Business Case | R | Analysis |  |  |  |  | 2018-11-13
Prototype | R | Analysis |  |  |  |  | 2018-11-13
etc. . .
Key Issues
Description |  | Status | Resolution/Update |  |  |  | Owner
Need clarification on project scope |  | G | We will meet with the client to go over the requirements of this project. |  |  |  | Client
Planned Accomplishments
Next week we plan to meet with the client and do some requirements building. After, we will get started on creating the Data and Process model.
Note on B46: Key Issues are issues that need your CM Director-level understanding and awareness.