## Status Summary
Project Dashboard
Note: Project plan with original dates and actual dates should be attached. | [6 empty] | Date: | 2018-10-02
Project Name: | TryVitris Capstone Project | [5 empty] | Project Status: | Y
Project Description: | Vitris clients need to consolidate and simplify customer interactions by implementing a member platform for sales, billing, customer service and field service requests. Currently, Vitris clients communicate with customers using email and web forms. Customers must re-enter their contact information each time they visit a client’s site. Additionally, Vitris clients must forward the customer request to the appropriate department prior to handling. By providing clients with a member platform, their customers can perform a variety self-service tasks, as well as gain greater insight into their purchases and client communication. Customers will be able to enter their own information into the CRM databases, reducing Vitris clients’ administrative workload. This new feature will expand Vitris’ current product offering, enabling them to deepen the relationships they have with existing clients.
Customer | Jack Perotta, President CEO of Vitris
Project Core Team: | Chandni Antala, Ariana Castaneda, Sarita Cini, Fatimata Sall
Next Milestone: | Brainstorming, Design the prototyping (Technical Architecture)
Phase Status
| Status | Plan |  | Status | Plan |  | Status | Date
Analysis | Y | 2018-10-02 | Testing | R | 2018-11-13
Design | R | 2018-10-23 | Installation | R | 2018-12-04
Construction | R | 2018-11-06
Leading Indicators | Status |  |  | Status |  |  | Status
On-Time | G | On-Budget |  | G | Delivery to Scope |  | Y
Major Accomplishments/Decisions
We have created a Data Model, Business Process, Systems Architecture, and Business Case. Modifications will be made as we move forward. Our next accomplishment is brainstorm and start designing our prototype.
CURRENT KEY ACTIVITIES --- NOTE ACTUAL (VS PROJECTED) DATES ARE INDICATED BY ITALICS
|  |  |  | START |  |  | END
Current Key Activities | STATUS |  | PHASE | PLAN | ACT | Comments | PLAN | ACT
Project Charter | G | Analysis |  | 2018-09-06 | 2018-09-12 |  | 2018-09-13 | 2018-09-13
Project Deck | G | Analysis |  | 2018-09-06 | 2018-09-13 |  | 2018-09-13 | 2018-09-13
Process Model | G | Analysis |  | 2018-09-24 | 2018-09-28 |  | 2018-09-27 | 2018-10-02
Data Model | G | Analysis |  | 2018-09-24 | 2018-09-28 |  | 2018-09-27 | 2018-10-02
System Architecture Design | G | Analysis |  | 2018-09-24 | 2018-09-28 |  | 2018-09-27 | 2018-10-02
Progress Report | Y | Analysis |  | 2018-09-29 | 2018-10-01 |  | 2018-09-27 | 2018-10-02
Business Case | Y | Analysis |  |  |  |  | 2018-11-13
Prototype | R | Analysis |  |  |  |  | 2018-11-13
etc. . .
Key Issues
Description |  | Status | Resolution/Update |  |  |  | Owner
Finding a common denominator between industry focus |  | G | Research and collaboration as a team to identify a key factor that can tell a story and fit all industries. |  |  |  | Team
Planned Accomplishments
Next week we plan to meet with the client for our second interview, visit Vitris' office and request a demo. We also will start a few brainstorming sessions, identify key challenges, and start our first draft of prototype.
Note on B46: Key Issues are issues that need your CM Director-level understanding and awareness.