## Status Summary
Project Dashboard
Note: Project plan with original dates and actual dates should be attached. | [6 empty] | Date: | 2018-11-06 | Y | Yes
Project Name: | TryVitris Capstone Project | [5 empty] | Project Status: | Y | N | No
Project Description: | Vitris clients need to consolidate and simplify customer interactions by implementing a member platform for sales, billing, customer service and field service requests. Currently, Vitris clients communicate with customers using email and web forms. Customers must re-enter their contact information each time they visit a client’s site. Additionally, Vitris clients must forward the customer request to the appropriate department prior to handling. By providing clients with a member platform, their customers can perform a variety self-service tasks, as well as gain greater insight into their purchases and client communication. Customers will be able to enter their own information into the CRM databases, reducing Vitris clients’ administrative workload. This new feature will expand Vitris’ current product offering, enabling them to deepen the relationships they have with existing clients. | [7 empty] | I | In Progress
[9 empty] | C | Completed
Customer | Jack Perotta, President CEO of Vitris
Project Core Team: | Chandni Antala, Ariana Castaneda, Sarita Cini, Fatimata Sall
[9 empty] | U | Unresolved
[9 empty] | R | Resolved
Next Milestone: | Working on the Prototype and Use Cases & Scenarios
Phase Status
| Status | Plan |  | Status | Plan |  | Status | Date
Analysis | G | 2018-10-02 | Testing | R | 2018-11-13
Design | G | 2018-10-23 | Installation | R | 2018-12-04
Construction | Y | 2018-11-06
Leading Indicators | Status |  |  | Status |  |  | Status
On-Time | G | On-Budget |  | G | Delivery to Scope |  | Y
Major Accomplishments/Decisions
We have created the first version of the prototype. We have also met with the client and confirmed if the models and brainstormed prototype was in line with the project scope.
CURRENT KEY ACTIVITIES --- NOTE ACTUAL (VS PROJECTED) DATES ARE INDICATED BY ITALICS
|  |  |  | START |  |  | END
Current Key Activities | STATUS |  | PHASE | PLAN | ACT | Comments | PLAN | ACT
Project Charter | G | Analysis |  | 2018-09-06 | 2018-09-12 |  | 2018-09-13 | 2018-09-13
Project Deck | G | Analysis |  | 2018-09-06 | 2018-09-13 |  | 2018-09-13 | 2018-09-13
Process Model | G | Analysis |  | 2018-09-24 | 2018-09-28 |  | 2018-09-27 | 2018-10-02
Data Model | G | Analysis |  | 2018-09-24 | 2018-09-28 |  | 2018-09-27 | 2018-10-02
System Architecture Design | G | Analysis |  | 2018-09-24 | 2018-09-28 |  | 2018-09-27 | 2018-10-02
Progress Report | Y | Analysis |  | 2018-09-29 | 2018-10-01 |  | 2018-09-27 | 2018-10-02
Business Case | Y | Analysis |  |  |  |  | 2018-11-13
Prototype | Y | Construction |  | 2018-10-16 | 2018-10-18 |  | 2018-11-13
etc. . .
Key Issues
Description |  | Status | Resolution/Update |  |  |  | Owner
Finding a common denominator between industry focus |  | G | Research and collaboration as a team to identify a key factor that can tell a story and fit all industries. |  |  |  | Team
Deciding what prototype design to go forward with from |  | G | The team will have to meet with the client to see what idea and design he would like the best. |  |  |  | Team
Avoiding feature and scope creep with the prototype. |  | Y | We will have to keep in the scope and main functionalities in mind while creating the prototype. If there is feature creep we will have to go back and fix it. |  |  |  | Team
Planned Accomplishments
Next week we plan to continue to build the prototype and keep the design and functionality within scope. We also plan to finalize the models and diagrams we created.
Note on B46: Key Issues are issues that need your CM Director-level understanding and awareness.