## Slide 1: Active Directory Audit
Kevin Berg
Matthew Dampf
Adam Joskowicz
Mahroo Sanatimehrizi
Notes: To change the image on this slide, select the picture and delete it. Then click the Pictures icon in the placeholder to insert your own image.

## Slide 2: Active Directory: Technology Background
Microsoft’s Directory Services Technology
Manage User Accounts, PCs, Servers
Enables easier management of secure environment

## Slide 3: Active Directory: Audit Objective
Internal Audit Role
Evaluation of AD Implementation
Independent assessment of control effectiveness

## Slide 4: Active Directory: Audit Scope
  In Scope
  Active Directory Management
  Secure Active Directory Boundaries
  Domain Controllers
  Domain and domain controller settings
  Administrative Practices

## Slide 5: Active Directory: Audit Scope
  Out of Scope
  Windows Server Configurations
  Workstations
  User Access
  DNS

## Slide 6: Active Directory: Risk Assessment
Possible Changes since last audit
New Technology
Change in Processes
Change in Structure
Risk | Impact | Likelihood | Inherent Risk
Privileged Access | Significant | Probable | High
Security Configuration | Significant | Probable | High
Design and Build | Significant | Probable | High

## Slide 7: Active Directory: Testing Approach
  Focus Areas
  Account Management
  Group Management
  Unit Management
  Schema Management
  Configuration Management
  Physical Security

## Slide 8: Active Directory: Roles and Responsibilities
  Auditor in Charge: Matthew Dampf
  Finance Manager: Mahroo Sanatimehrizi
  Information Technology Auditor: Kevin Berg
  IT Risk and Assurance Manager: Adam Joskowicz

## Slide 9: Active Directory: Key Dates and Deliverables
Planning | Start Notice | February 23, 2018
 | Kick-Off Meeting | April 9, 2018
Field work | Field work start | April 9, 2018
Review | Field work finish | June 10. 2018
Reporting | Findings Grid to IT Audit VP | June 23, 2018
 | Findings Grid to Client | June 30, 2018
 | Draft Report | July 17, 2018
 | Exit Meeting | July 24, 2018
 | Final Report | July 31, 2018

## Slide 10: Active Directory: Audit Hours
Phase | Time | Percentage of Time
Planning | 6 weeks | 32%
Testing | 8 weeks | 42%
Reporting | 5 weeks | 26%
Total | 21 weeks | 100%

## Slide 11: Active Directory: Hours by Employee
Chart: 
| Auditor in Charge | Finance Manager | IT Auditor | IT Risk and Assurance
Planning | 1 | 0.8 | 0.33 | 0.8
Testing | 0.33 | 0.7 | 1 | 0.6
Reporting | 1 | 0.5 | 0.2 | 0.8