## Status Summary
Project Dashboard
Note: Project plan with original dates and actual dates should be attached. | [6 empty] | Date: | 2016-04-05
Project Name: | New Kid application | [5 empty] | Project Status: | G
Project Description: | Our app/website, New Kid, will provide a resource for people moving to a new area or considering multiple areas to move to. It will allow users to compare various dimensions (job prospects, cost of living, climate, entertainment, etc.) across multiple cities. New Kid will have a community environment allowing users to share advice and tips about the moving process or specific locations.
Customer
Project Core Team: | Maggie Scanlon, Lauren Sirianni, Tyler Nelson, Dominic Sambucci
Next Milestone: | Prototype
Phase Status
| Status | Plan |  | Status | Plan |  | Status | Date
Analysis | G | 2016-02-07 | Testing | G | 2016-03-08
Design | G | 2016-02-17
Construction | G | 2016-03-01
Leading Indicators | Status |  |  | Status |  |  | Status
On-Time | G | On-Budget |  | Y | Delivery to Scope |  | G
Major Accomplishments/Decisions
The project website was built and the project charter was also completed. Project website was further edited to display team members and roles within the group.
CURRENT KEY ACTIVITIES --- NOTE ACTUAL (VS PROJECTED) DATES ARE INDICATED BY ITALICS
|  |  |  | START |  |  | END
Current Key Activities | STATUS |  | PHASE | PLAN | ACT | Comments | PLAN | ACT
Discussion/General Plan | G | Analysis |  | 2005-02-07 | 2016-02-07 |  | 2016-02-07 | 2016-02-07
Prototype Layout | G | Analysis |  | 2016-02-17 |  |  | 2016-02-17
UI Mockup | G | Design
--- User login | G | Design |  | 2016-02-19 |  |  | 2016-02-23
--- Main Menu | G | Design |  | 2016-02-23 |  |  | 2016-03-01
--- Salary Converter | G | Design |  | 2016-02-23 |  |  | 2016-03-01
--- City Comparison | G | Design |  | 2016-02-27 |  |  | 2016-03-03
Prototype Revision | Y |  |  | 2016-03-10 |  |  | 2016-03-10
Key Issues
Description |  | Status | Resolution/Update |  |  |  | Owner
Final edits need to be done to prototype |  | G | Extra time has been added to schedule for next week |  |  |  | Lauren and Maggie
Finalize personas |  | G | Team meeting has been scheduled to finalize personas and make appropriate changes to the protoype accordingly |  |  |  | Team
Planned Accomplishments
Create presentation slide deck, finish documentation
Note on B46: Key Issues are issues that need your CM Director-level understanding and awareness.