## Status Summary
Project Dashboard
Note: Project plan with original dates and actual dates should be attached. | [6 empty] | Date: | 2016-04-11
Project Name: | New Kid application | [5 empty] | Project Status: | G
Project Description: | Our app/website, New Kid, will provide a resource for people moving to a new area or considering multiple areas to move to. It will allow users to compare various dimensions (job prospects, cost of living, climate, entertainment, etc.) across multiple cities. New Kid will have a community environment allowing users to share advice and tips about the moving process or specific locations.
Customer
Project Core Team: | Maggie Scanlon, Lauren Sirianni, Tyler Nelson, Dominic Sambucci
Next Milestone: | Prototype
Phase Status
| Status | Plan |  | Status | Plan |  | Status | Date
Analysis | G | 2016-02-07 | Testing | G | 2016-03-08
Design | G | 2016-02-17
Construction | G | 2016-03-01
Leading Indicators | Status |  |  | Status |  |  | Status
On-Time | G | On-Budget |  | G | Delivery to Scope |  | G
Major Accomplishments/Decisions
Prototype and personas were completed. Presentation deck is started
CURRENT KEY ACTIVITIES --- NOTE ACTUAL (VS PROJECTED) DATES ARE INDICATED BY ITALICS
|  |  |  | START |  |  | END
Current Key Activities | STATUS |  | PHASE | PLAN | ACT | Comments | PLAN | ACT
Discussion/General Plan | G | Analysis |  | 2005-02-07 | 2016-02-07 |  | 2016-02-07 | 2016-02-07
Prototype Layout | G | Analysis |  | 2016-02-17 |  |  | 2016-02-17
UI Mockup | G | Design
--- User login | G | Design |  | 2016-02-19 |  |  | 2016-02-23
--- Main Menu | G | Design |  | 2016-02-23 |  |  | 2016-03-01
--- Salary Converter | G | Design |  | 2016-02-23 |  |  | 2016-03-01
--- City Comparison | G | Design |  | 2016-02-27 |  |  | 2016-03-03
Prototype Revision | G |  |  | 2016-03-10 |  |  | 2016-03-10
Key Issues
Description |  | Status | Resolution/Update |  |  |  | Owner
Finish revising deck and practice presentation |  | G | Team has scheduled two meetings to complete task |  |  |  | Team
Ensure that all items are uploaded to team site |  | G | Team will communicate via email to make sure all documentation is complete |  |  |  | Lauren
Planned Accomplishments
Complete presentation, complete team site
Note on B46: Key Issues are issues that need your CM Director-level understanding and awareness.