## Status Summary
Project Dashboard
Note: Project plan with original dates and actual dates should be attached. | [6 empty] | Date: | 2016-02-09
Project Name: | New Kid application | [5 empty] | Project Status: | G
Project Description: | Our app/website, New Kid, will provide a resource for people moving to a new area or considering multiple areas to move to. It will allow users to compare various dimensions (job prospects, cost of living, climate, entertainment, etc.) across multiple cities. New Kid will have a community environment allowing users to share advice and tips about the moving process or specific locations.
Customer
Project Core Team: | Maggie Scanlon, Lauren Sirianni, Tyler Nelson, Dominic Sambucci
Next Milestone: | Prototype
Phase Status
| Status | Plan |  | Status | Plan |  | Status | Date
Analysis | G | 2016-02-07 | Testing | Y | 2016-03-08
Design | Y | 2016-02-17
Construction | Y | 2016-03-01
Leading Indicators | Status |  |  | Status |  |  | Status
On-Time | G | On-Budget |  | G | Delivery to Scope |  | G
Major Accomplishments/Decisions
The project website was built and the project charter is almost completed.
CURRENT KEY ACTIVITIES --- NOTE ACTUAL (VS PROJECTED) DATES ARE INDICATED BY ITALICS
|  |  |  | START |  |  | END
Current Key Activities | STATUS |  | PHASE | PLAN | ACT | Comments | PLAN | ACT
Discussion/General Plan | G | Analysis |  | 2005-02-07 | 2016-02-07 |  | 2016-02-07 | 2016-02-07
Prototype Layout | Y | Analysis |  | 2016-02-17 |  |  | 2016-02-17
UI Mockup | Y | Design
--- User login | Y | Design |  | 2016-02-19 |  |  | 2016-02-23
--- Main Menu | Y | Design |  | 2016-02-23 |  |  | 2016-03-01
--- Salary Converter | Y | Design |  | 2016-02-23 |  |  | 2016-03-01
--- City Comparison | Y | Design |  | 2016-02-27 |  |  | 2016-03-03
Prototype Revision | Y |  |  | 2016-03-10 |  |  | 2016-03-10
Key Issues
Description |  | Status | Resolution/Update |  |  |  | Owner
Team Members and Roles must be added to website |  | G | Resource assigned to complete this week |  |  |  | Lauren
Project Charter must be finalized |  | G | Group will meet to complete charter |  |  |  | Group
Planned Accomplishments
Begin designing prototype layout
Note on B46: Key Issues are issues that need your CM Director-level understanding and awareness.