## Status Summary
Project Dashboard
Note: Project plan with original dates and actual dates should be attached. | [6 empty] | Date: | 2017-02-02
Project Name: | Newsance Project | [5 empty] | Project Status: | G
Project Description: | In a fast paced and modern world, people have limited time to pay attention to what is happening around them in the world. Given the constant movement, stories are constantly added and updated the second that information is released and it can be tough for an individual to distinguish what is true from the false stories. Our system will aggregate multiple reliable news sources and condense them in a fashion that fits into each user’s busy and hectic lifestyle while avoiding objectively false or misleading articles. A user can choose what topics of news they would like to read about and how wide of a scope of news they want to see. Through this, a person is not distracted from their busy life but remain informed as to what is going on around them.
Customer | General Public; People living a busy lifestyle with limited time ot stay connected
Project Core Team: | Brandan Mackowsky, Will Agentowicz, Eugene Tartaglione, Adama Traore
Next Milestone: | Finish last stages of analysis and continue working on application design
Phase Status
| Status | Plan |  | Status | Plan |  | Status | Date
Analysis | G | 2017-02-02 | Testing | G | 2017-03-15 |  | G
Design | G | 2017-02-15 | Installation | G | 2017-04-01
Construction | G | 2017-03-01
Leading Indicators | Status |  |  | Status |  |  | Status
On-Time | G | On-Budget |  | G | Delivery to Scope |  | G
Major Accomplishments/Decisions
At the current point, our largest accomplishment was finaliing our idea so that the planning phase could truely be initiated. Through this, we can conduct planning the project, start the analytics phase, and move our way into the design of the prototype. Larger decisons we made were allocating who will be in command for each specific section of the project as it moves forward as well as how long we expect dates of the project to go on. We also completed the project charter for the idea proposal. We discussed and figured out some of the smaller details regarding the business model and what the main purpose of the application will be.
CURRENT KEY ACTIVITIES --- NOTE ACTUAL (VS PROJECTED) DATES ARE INDICATED BY ITALICS
|  |  |  | START |  |  | END
Current Key Activities | STATUS |  | PHASE | PLAN | ACT | Comments | PLAN | ACT
Test plan | G | Planning |  | 2017-02-02 | 2017-02-01 |  | 2017-02-07 | N/A
Final project plan | G | Analysis |  | 2017-02-07 | N/A |  | 2017-02-14 | N/A
UI Mockup | G | Design
--- User login | G | Design |  | 2017-02-14 | N/A |  | 2017-02-28 | N/A
--- Account maintenance | G | Design |  | 2017-02-14 | N/A |  | 2017-02-28 | N/A
--- Account preferences | G | Design |  | 2017-02-14 | N/A |  | 2017-02-28 | N/A
--- Sources | G | Design |  | 2017-02-14 | N/A |  | 2017-02-28 | N/A
--- User Dashboard | G | Design |  | 2017-02-14 | N/A |  | 2017-02-28 | N/A
Key Issues
Description |  | Status | Resolution/Update |  |  |  | Owner
Original Project Idea - Too Much Competition |  | G | We generated a new idea that works better for the project duration |  |  |  | Brandan/Will
Group buy-in for the project |  | Y | Encourage other members to participate |  |  |  | Brandan/Will
Planned Accomplishments
Next week we plan on developing a wireframe to determine what we want the application design/layout to look like. Also need to incorporate some of the ideas from the class into our project. Plan on researching similar apps (Flipboard) to see how we can differentiate ourselves from our competitors.
Note on B46: Key Issues are issues that need your CM Director-level understanding and awareness.