## Status Summary
Project Dashboard
Note: Project plan with original dates and actual dates should be attached. | [6 empty] | Date: | 2017-03-09
Project Name: | Newsance Project | [5 empty] | Project Status: | G
Project Description: | In a fast paced and modern world, people have limited time to pay attention to what is happening around them in the world. Given the constant movement, stories are constantly added and updated the second that information is released and it can be tough for an individual to distinguish what is true from the false stories. Our system will aggregate multiple reliable news sources and condense them in a fashion that fits into each user’s busy and hectic lifestyle while avoiding objectively false or misleading articles. A user can choose what topics of news they would like to read about and how wide of a scope of news they want to see. Through this, a person is not distracted from their busy life but remain informed as to what is going on around them.
Customer | General Public; People living a busy lifestyle with limited time to stay connected
Project Core Team: | Brandan Mackowsky, Will Agentowicz, Eugene Tartaglione, Adama Traore
Next Milestone: | Complete data schema, sytem architecture, and project website
Phase Status
| Status | Plan |  | Status | Plan |  | Status | Date
Analysis | G | 2017-02-02 | Testing | G | 2017-03-15
Design | G | 2017-02-15 | Installation | G | 2017-04-01
Construction | G | 2017-03-01
Leading Indicators | Status |  |  | Status |  |  | Status
On-Time | G | On-Budget |  | G | Delivery to Scope |  | G
Major Accomplishments/Decisions
This week we made changes to the project charter to accurately reflect our updated business model. We plan on having a free and unlimited news application instead of limiting users to a set number of articles. Instead, we will place ads in the free verison of the application. Also, there will be a premium subscription where users are able to access articles from sources like the Wall Street Journal and The Economist, which we will partner with to get through their paywall. Also, we will have daily audio podcasts that summarize the news similarly to the news feed, allowing users to digest the news in a different format, which will also have ads.
CURRENT KEY ACTIVITIES --- NOTE ACTUAL (VS PROJECTED) DATES ARE INDICATED BY ITALICS
|  |  |  | START |  |  | END
Current Key Activities | STATUS |  | PHASE | PLAN | ACT | Comments | PLAN | ACT
Test plan | G | Planning |  | 2017-02-02 | 2017-02-03 |  | 2017-02-07 | 2017-02-07
Final project plan | G | Analysis |  | 2017-02-07 | N/A |  | 2017-02-14 | 2017-02-17
UI Mockup | G | Design
--- User login | G | Design |  | 2017-02-14 | 2017-02-16 |  | 2017-02-28 | 2017-03-02
--- Account maintenance | G | Design |  | 2017-02-14 | 2017-02-16 |  | 2017-02-28 | 2017-03-02
--- Account preferences | G | Design |  | 2017-02-14 | 2017-02-16 |  | 2017-02-28 | 2017-03-02
--- Sources | G | Design |  | 2017-02-14 | 2017-02-16 |  | 2017-02-28 | 2017-03-02
--- User Dashboard | G | Design |  | 2017-02-14 | 2017-02-16 |  | 2017-02-28 | 2017-03-02
Key Issues
Description |  | Status | Resolution/Update |  |  |  | Owner
Original Project Idea - Too Much Competition |  | G | We generated a new idea that works better for the project duration |  |  |  | Brandan/Will
Group buy-in for the project |  | Y | Encourage other members to participate |  |  |  | Brandan/Will
Planned Accomplishments
Next week we plan on completing the data schema and systems architecture for Newsance. Also, we are going to build the project site on the community website. We will begin creating a JustInMind prototype that acts as an example as to how the application would look and function based on our planned designs.
Note on B46: Key Issues are issues that need your CM Director-level understanding and awareness.