## Sheet1
Project Dashboard
Note: Project plan with original dates and actual dates should be attached. | [6 empty] | Date: | 2016-03-22
Project Name: | OuttaTowner | [5 empty] | Project Status: | G
Project Description: | Our application will allow foreign travellers and locals the opportunity to meet up for the purpose of practicing each other's languages and to show the traveller the culture of the foreign country.
Customer | Average foreign traveler
Project Core Team: | Eric Samuels, Marcos Jordan, Julia Knable
Next Milestone: | Additional features for prototype and futher discussion of deliverables.
Phase Status
| Status | Plan |  | Status | Plan |  | Status | Date
Analysis | G | 2016-03-15 | Testing | Y | 2016-04-10
Design | G | 2016-03-20 | Installation | R | 2016-04-15
Construction | G | 2016-03-28
Leading Indicators | Status |  |  | Status |  |  | Status
On-Time | G | On-Budget |  | G | Delivery to Scope |  | G
Major Accomplishments/Decisions
Marcos is finalizing the protoype. Julia is almost done the budget and Eric is close to completing the core documents for the final presentaiton.
CURRENT KEY ACTIVITIES --- NOTE ACTUAL (VS PROJECTED) DATES ARE INDICATED BY ITALICS
|  |  |  | START |  |  | END
Current Key Activities | STATUS |  | PHASE | PLAN | ACT | Comments | PLAN | ACT
Project Charter | G | Revision |  | 2016-02-02 | 2016-02-09 |  | 2005-02-15 | 2005-02-15
Prototype | Y | Initial phase |  | 2016-02-15 | 2016-02-15 | Template | 2016-04-19
Budget | Y | Revision |  | 2016-02-15 | 2016-02-15 | Need to finalize some numbers | 2016-04-18
Key Issues
Description |  | Status | Resolution/Update |  |  |  | Owner
We're having trouble creating a datamaster for our prototype. Once we complete this, our protoype will be completed |  | Y | Still working on resolving this problem |  |  |  | All
Backing up Budget with Data |  | G | Julia still needs to find some examples of budget numbers to base our budget off of. |  |  |  | Julia
Planned Accomplishments
Justinmind issues have been resolved. The budget will hopefully be completed by next week.
Note on A45: Key Issues are issues that need your CM Director-level understanding and awareness.