## Sheet1
Project Dashboard
Note: Project plan with original dates and actual dates should be attached. | [6 empty] | Date: | 2016-04-05
Project Name: | OuttaTowner | [5 empty] | Project Status: | G
Project Description: | Our application will allow foreign travellers and locals the opportunity to meet up for the purpose of practicing each other's languages and to show the traveller the culture of the foreign country.
Customer | Average foreign traveler
Project Core Team: | Eric Samuels, Marcos Jordan, Julia Knable
Next Milestone: | Additional features for prototype and futher discussion of deliverables.
Phase Status
| Status | Plan |  | Status | Plan |  | Status | Date
Analysis | G | 2016-03-15 | Testing | Y | 2016-04-10
Design | G | 2016-03-20 | Installation | R | 2016-04-15
Construction | G | 2016-03-28
Leading Indicators | Status |  |  | Status |  |  | Status
On-Time | G | On-Budget |  | G | Delivery to Scope |  | G
Major Accomplishments/Decisions
The protoype has been finalized. There are still a few key details that need to be finalized. Eric is out of the country so we had to delay making some key decisions.
CURRENT KEY ACTIVITIES --- NOTE ACTUAL (VS PROJECTED) DATES ARE INDICATED BY ITALICS
|  |  |  | START |  |  | END
Current Key Activities | STATUS |  | PHASE | PLAN | ACT | Comments | PLAN | ACT
Project Charter | G | Revision |  | 2016-02-02 | 2016-02-09 |  | 2005-02-15 | 2005-02-15
Prototype | G | Final Phases |  | 2016-02-15 | 2016-04-05 | Almost completed | 2016-04-19
Budget | G | Revision |  | 2016-02-15 | 2016-02-15 | Finished | 2016-04-05
Key Issues
Description |  | Status | Resolution/Update |  |  |  | Owner
We are having trouble of deciding on which persona to present for our final presentaiton |  | Y | Still working on resolving this problem |  |  |  | All
Eric had to leave the country for a family issue |  | Y | He's still away |  |  |  | Eric
Planned Accomplishments
Protoype is pretty much finalized. Budget is completed. Next steps include finlaizing the final project
Note on A45: Key Issues are issues that need your CM Director-level understanding and awareness.