## Status Summary
Project Dashboard
Note: Project plan with original dates and actual dates should be attached. | [6 empty] | Date: | 2018-03-29
Project Name: | Owl Explore | [5 empty] | Project Status: | G
Project Description: | New students, transfer students, foreign exchange students, and visitors of Temple University often have a difficult time locating academic buildings and other destinations within or surrounding Temple’s main campus. A PDF map of the campus is provided through the university website but is outdated and confusing to use by many. This project will develop an easy to use, interactive map of Temple University’s main campus and the immediate surrounding area. The finished product will allow anyone to conveniently locate and navigate to their desired destination through the app.
Customer | New Students, Current Students, Foreign Exchange Students, and visitors of Temple university
Project Core Team: | Nicholas Gormley, Shihao Fei, Ryan Tempestini, Thomas Murphy
Next Milestone: | Revised prototype and documentation, Creation of team project site
Phase Status
| Status | Plan |  | Status | Plan |  | Status | Date
Analysis | G | 2018-01-30 | Testing | G | 2018-04-20
Design | G | 2018-02-14 | Installation | G | 2018-04-24
Construction | G | 2018-03-01
Leading Indicators | Status |  |  | Status |  |  | Status
On-Time | G | On-Budget |  | G | Delivery to Scope |  | G
Major Accomplishments/Decisions
Since our last status report (3/20), we have mainly been focusing on developing our prototype and revising our documentation such as the data model, process model and system architecture diagram. We have also created a project site on the Temple MIS Community domain in order to post our accomplishments and give background on our project team. We have kept in contact with our mentor and have been receiving positive feedback from his end. We are set to meet again with him at the end of next week.
CURRENT KEY ACTIVITIES --- NOTE ACTUAL (VS PROJECTED) DATES ARE INDICATED BY ITALICS
|  |  |  | START |  |  | END
Current Key Activities | STATUS |  | PHASE | PLAN | ACT | Comments | PLAN | ACT
Project Business Model | G | Analysis |  | 2018-03-14 | 2018-03-19
Project Business Case (spreadsheet) | G | Analysis |  | 2018-03-14 | 2018-03-19
Prototype Rough Draft | G | Design |  | 2018-03-14 | 2018-03-19
Key Issues
Description |  | Status | Resolution/Update |  |  |  | Owner
An interactive map was already created by a third party website. |  | G | The university is still in need of an interactive map because they do not have access to this map, which is outdated and owned by an outside domain. This map will not be used by Temple University after this semester. |  |  |  | Nicholas Gormley, Shihao Fei, Ryan Tempestini, Thomas Murphy
Planned Accomplishments
By next status report (4/10), we plan to have a final draft of our prototype, completed documentation, and an updated project site. Given that the end of our project is near, we will be dedicating lots of time in the next couple weeks to have the best possible solution at project completion.
Note on B46: Key Issues are issues that need your CM Director-level understanding and awareness.