## Executive Summary
Owl Insider aims to create a more interactive college experience for non-traditional students. With this app, transfer students, commuter students, and all other students who are overwhelmed with the challenges of attending a large university are able to fill out the "Owl Insider Questionnarie," which includes their Major, Graudation Year, Class Roster, and individual interests. The questionnaire will then take the inputs, calculate the results using our algorithm and output a unique list of activities and events they may be interested in. It will also show fellow students with both similar interests and/or classes who the student may be able to get into contact with. The Owl Insider app will be track students location on campus, so after they have used the app for a certain amount of time, it will be able to learn the student's patterns. This will help tailor the app to students and push certain events happening that day specifically tailored for that individual. We profit from this platform by retaining our universities most "at-risk" students and increasing Temple's graduation rates.

## Finance
1. Financial Analysis
| Semester 1 Hours | Semester 2 Hours | Semester 3 Hours | Notes: Because there are no charges, we will track the hours it will take to complete the project. We have calculated the hypothetical costs of outsourcing the work for this project. The average cost for application design is $100/hour. The average cost for application development is $59/hour. And the average cost for application testing ad development is $50/hour. We estiamte that it will cost atleast $15,000 per year to host all of the user information for the application Owl Insider, if we were to go outside of Temple University. Sources: https://yalantis.com/blog/how-much-does-it-cost-to-design-an-app/ https://www.comentum.com/web-development-cost-rate-comparison.html https://apptestnow.com/en/pricing-and-process/
Planning and Design (16 week semester at 3.5 hours a week) | 56 | - | -
Building Owl Insider (16 week semester at 3.5 hours a week) | - | 56 | -
Implementation and Beta Testing of Owl Insider (16 week semester at 7 hours a week) | - | - | 112
Total Hours Worked | 224
Total Cost of Workers | $ -
Total Cost to Deploy on Temple's Network | $ -
Because we are building and maintaining the application through Temple's resources, brining Owl Insider to life will cost no money. We did, however, track how many hours it will take to build the app. Below, we have accounted for how much building Owl Insider would cost if we had went outside of Temple.
Expenses | Year 1 | Year 2 | Year 3
App Design | 5600 | - | -
App Development | 3304 | - | -
Testing and Deployment | 5600 | - | -
Cloud Services | 15000 | 15000 | 15000
Total Per Year | 29504 | 15000 | 15000
Total Cost for Project | 59504

## Project Definition
1. Background Information
We have done a lot of research for Temple University's retention rate and while 90% of students are retained at Temple, that doesn't explain to what happened to the "at risk" students. When we say "at risk" this can mean anything from students who can't afford school, who have personal problems affecting their education, or students who are considering leaving the university for other reasons. These student may also be known as "non-completers." From a survey of almost 2,000 non-completers from Temple, we found that around 1300 have transferred and the remaining had dropped out alltogether. We also have found that temple's graduation rate is 45%. The national graduation average is 60%. We are extremely below the national average. Now, we may not be able to do anything for the ones who dropped out, but the 1300 that transferred, what could have been done differently for them to stay? That is where Owl Insider comes in. Source: https://www.collegefactual.com/colleges/temple-university/academic-life/graduation-and-retention/
2. Business Objective
Our objective with Owl Insider is to retain those transferring students and increase Temple's graduation rate. We want to make their college experience at Temple University as interactive and efficient as possible. We want to make sure they are not getting lost within the 30,000 undergraduate student population and that they are enjoying their, on average, four college years as much as they possibly can at Temple. We will need the Owl Insider application to be used by all incoming students and if it is successful, we will be able to retain the students who may have considered transferring before and get them to graduate on track for a four-year graduation.
3. Benefits and Limitations
Benefits | Limitations
Improve retention rate | Students migh not use it
Generate more revenue | Expensive to create
Remain competitive as a University | Difficult to maintain
Improve student morale
4. Option Identification and Selection
The problem we are looking to solve is to retain "at-risk" students in out student population, at Temple University and increase the graduation rate. We will be using Machine Learning and Geolocation in our application to do just that. The app will learn the interests of the student after they fill out the questionnaire. Once they have been using the app for some time, Owl Insider will learn the interest of the student and the places on campus they frequently visit. In learning this, the app will be able to show the student other students with similar interests and/or classes, student organizations to join, and events that they can take part in. Also, when they are entering certain building, the geolocation will recognize where they are and push events for the day in that building, based off of their questionnaire results. Other possible solutions for the retention problem would be having the advisors be in contact with these "at-risk" students and helping them with any problems they may have, using the apps currently supplies through the univeristiy (Owlconnect, TUmobile, etc.), and doing nothing. We believe out option, Owl Insider, is the best option because it allows the students to actively figure out what their problems may be and come into contact with students who have similar problems. If we left the problem solely on the advisors, there would be too many students to keep track of and they would never be able to fix the problem entirely. Also, our solution is better than doing nothing because we are making an attempt to retain those students. By doing nothing, we would guarantee that those "at-risk" students who were going to leave are, in fact, definitely leaving Temple.
5. Scope, Impact, and Interdependencies
With Owl Insider, our project scope and boundaries would be for the transfer, commuter, freshman, and "at-risk" students on campus. While anyone can use the app, those are the students we are aiming to target. The student can download the app and sign in with their TU credentials, which will populate the questionnaire with their TUportal-supplied information (Graduation Year, Major, Class Roster). The student will supply all other personal information (i.e. personal interests, need for study groups, etc.). We will not be excluding any student from using the application. The impact of Owl Insider will be to connect students in ways they would not have connected before using the application so they feel they are prepared for graduation. They are able to connect with fellow students, student organizations, and campus events that will help their college experience improve enough for them to want to stay and finish their degrees at Temple University. There is one significant interdependency with Owl insider. We have to have multiple students using the app in order to connect the students, based on their classes and interests. Without having multiple students, there would be no one to connect with. This app is also interdependent with TUportal in that it needs to be able to pull their college information (i.e. Graduatio Year, Major, Class Rosters, etc.)
6. Outline Plan
What is Required? | How is it done? | Who does it? | When will this be done?
Project Deck | It will have 12 slides describing our proposal in deatil. It will be done in Microsoft PowerPoint. | Lauren Soentgen | December 4th, 2018
Project Charter | We will submit a Project Charter deatiled in Microsoft Word. | All Project Managers/Business Analysts. | October 23rd, 2018
Project Budget | This will be a detailed overview of what it will cost to produce Owl Insider. It will be submitted in Microsoft Excel. | Rebecca Robinson | October 23rd, 2018
Data Model | This will be done to explain how Owl Insider uses the data within the Application. | Anthony Mignona | December 4th, 2018
Process Model | Our Process Model will explain how each process of our application works from begining to end. | Nina Sjostrom | December 4th, 2018
Systems Architecture Diagram | This will depict how our application is collecting the data. | All project Managers/Business Analysts | December 4th, 2018
Screen Prints of Prototype | This will be screenshots of how each page of our prototype works. It will be submitted with out final proposal. | Anthony Mignona | December 4th, 2018
Project Website | This will allow anyone who wants to learn about Owl Insider to take a look at our progress. It will be on the MIS Community Site, here at Temple University. | All project Managers/Business Analysts. | October 23rd, 2018
Prototype ready for Demonstration | Our prototype will be made in JustinMind. | Anthony Mignona | December 4th, 2018
Business Case | This will be a large overview of every aspect of the project. It will be submitted in Microsoft Excel. | Nina Sjostrom | October 23rd, 2018
7. Market Assessment
App Capabilities | Suitable | Owl Connect | TU Mobile | Owl Insider
Easy to Use Phone Application | ✓ | ✖ | ✓ | ✓
Find/Create Student Events (ex: study group) | ✖ | ✖ | ✖ | ✓
Student Network Connectivity | ✖ | ✖ | ✖ | ✓
Tailored Individuality when using the Application | ✖ | ✖ | ✖ | ✓
8. Risk Assessment
Risks Involved | Consequences of Risk | Plans to deal with Risk
Application takes longer then planned to develop | More expenses incurred | Stay on schedule
Cannot connect with TUportal | There is no way to guarantee the user is a Temple student | Mitigate the risk by allowing this risk not to happen
Students do not download app | There is no purpose for app in this case | Make it a mandatory app to download for all new students
Does not retain students like intended | Retention rate does not improve | Create a new purpose for the application
Project sponsor pulls out of project | Project will stop being created | Find a new project sponsor
9. Project Approach
We will plan everything in house for Owl Insider. The project managers/business analysts will be doing the research for the application. We then will supply this information to the CIS major class that will take on our project. We will work with them for any questions they may have. The CIS majors will then plan, deisgn, and a create the application. The project managers/business analysts will be in contact with the CIS majors on how the application will look. Temple University, however, will be the owner of the application. Once the application is finished, we will be in contact with Temple University computer services to have Owl Insider linked with TUportal, so that only the users of the application will be people with Temple credentials
10. Purchasing Strategy
The application itself will be free. Eveything will be designed, created, and testes in house by and for Temple students. CIS majors will create and Temple Computer Services will host it on Temple's network. We have calculated that if we had created this application outside of Temple Universitry, it would cost, approximately, $60,000. By staing within Temple, it will be free of charge.

## Project Organization
1. Project Governance
Stakeholder Register
Name | Title
Anthony Messina | Project Sponsor
Nina Sjostrom | Project Manager/Business Analyst
Lauren Soentgen | Project Manager/Business Analyst
Rebecca Robinson | Project Manager/Business Analyst
Anthony Mignona | Project Manager/Business Analyst
Decisions are made unanimously among the project managers/business analysts. We brainstorm and outline the porject and relay the information to our project sponsor.
2. Progress Reporting
To define our progress on the project, our project managers/business analysts meet together once weekly on saturday mornings. We debrief one another on our individual progress and make goals for the coming week. We work out any issues and make a list of questions we have for our project sponsor. Then, every Tuesday we meet with our project sponsor and ask our questions and compile the answers in our shared drive. During the remainder of the week, we work individually on our assinged parts and contact one another when necessary. We highlight our progress through a progress slide deck that is presented every week on the Tuesday meeting day.