## Status Summary
Project Dashboard
[7 empty] | Date: | 2017-02-16
Project Name: | Performance Evaluation and Wellness Program Integration | [5 empty] | Project Status: | G
Project Description: | According to Nielsen, 1 in 6 consumers in the United States currently owns a wearable, and the market is expected to continue growing. There is no shortage of wearable devices and related apps to collect data, and some companies have been able to generate insights by comparing aggregated employee health data to broad business goals, such as fewer manufacturing errors or lower employee turnover rates. This insight enables health risk and cost reduction while allowing organizations to modify wellness programs to better incentivize productive habits. Two companies specializing in this area are Vivametrica and Springbuk. Greater benefits are realized as employee engagement in wellness programs and the amount of subsequent data increases. Gartner estimates in 2018 wellness programs will drive 15% of total fitness tracker purchases in the United States. In addition to increasing use of wearables with wellness programs, a performance management trend towards more frequent performance evaluations, specifically among professional services and technology firms, provides an opportunity. A 2016 PwC Consumer Intelligence Series report found that 62% of consumers would find rewards for productivity improvements based on employer-monitored wearables to be useful. Based on these trends and indicated demand, we will address the connection between personal health habits and productivity using employer-sponsored health and wellness programs and performance evaluations. The solution will include a dashboard providing employees with information and insight to help balance personal health and habits with their performance at work. By providing employees with a tool to help manage work-life balance, this will increase engagement in the wellness programs and generate more information to assist organizations in risk and cost reduction for insurance.
Customer | HR Directors
Project Core Team: | Derek Gibbs, Eric Koek, Erika Nixon, David Yastremsky
Next Milestone: | Finalized Project Idea with Research and Draft of Business Case
Phase Status
| Status | Plan |  | Status | Plan |  | Status | Date
Analysis | Y | 2017-02-16 | Testing | G | 2017-04-13
Design | G | 2017-03-02 | Selling / Presenting | G | 2017-04-25
Construction | G | 2017-04-07
Leading Indicators | Status |  |  | Status |  |  | Status
On-Time | Y | On-Budget |  | G | Delivery to Scope |  | G
Major Accomplishments/Decisions
We conducted competition studies to ensure our product has a unique value proposition. We conducted a viability study to confirm that the technology for our product exists and the changes can be integrated. We created a business case for our clients. We interviewed potential business users in developing the business case. We decided to use a tiered pricing system to resolve differing needs in customer segments. We updated the project charter to reflect changes in our project.
CURRENT KEY ACTIVITIES --- NOTE ACTUAL (VS PROJECTED) DATES ARE INDICATED BY ITALICS
|  |  |  | START |  |  | END
Current Key Activities | STATUS |  | PHASE | PLAN | ACT | Comments | PLAN | ACT
Research functionality | G | Analysis |  | 2017-01-30 | 2017-01-30 | Redefining project resulted in additional need for analysis. | 2017-02-09
Research competition | Y | Analysis |  | 2017-01-30 | 2017-01-30 | Redefining project resulted in additional need for analysis. | 2017-02-09 | 2017-02-16
Finalize project | G | Analysis |  | 2017-02-09 | 2017-02-09 |  | 2017-02-16 | 2017-02-16
Create near-completed charter | G | Analysis |  | 2017-02-03 |  |  | 2017-03-02
UI Mockup | G | Design |  | 2017-02-23 |  |  | 2017-03-02
Determine data needs | G | Design |  | 2017-03-02 |  |  | 2017-03-16
Create project documents | G | Design |  | 2017-02-23 |  |  | 2017-03-16
Create prototype | G | Construction |  | 2017-02-28 |  |  | 2017-04-07
Test prototype | G | Testing |  | 2017-04-07 |  |  | 2017-04-13
Finalize documents | G | Selling / Presentation |  | 2017-03-23 |  |  | 2017-04-13
Prepare presentation | G | Selling / Presentation |  | 2017-04-13 |  |  | 2017-04-25
Key Issues
Description |  | Status | Resolution/Update |  |  |  | Owner
Planned Accomplishments
Next week, we will finish the preliminary research (viability & competition analyses) and finalize the project idea.