## Status Summary
Project Dashboard
[7 empty] | Date: | 2017-04-13
Project Name: | Performance Evaluation and Wellness Program Integration | [5 empty] | Project Status: | G
Project Description: | According to Nielsen, 1 in 6 consumers in the United States currently owns a wearable, and the market is expected to continue growing. In addition, Gartner estimates in 2018 wellness programs will drive 15% of total fitness tracker purchases in the United States. There is no shortage of wearable devices and apps to collect data from them, and some companies are starting to generate insights by comparing aggregated employee health data to broad business goals, such as fewer manufacturing errors or lower employee turnover rates. This insight enables health risk and cost reduction while allowing organizations to modify wellness programs to better incentivize productive habits. Two companies specializing in this area are Vivametrica and Springbuk. Greater benefits are realized as employee engagement in wellness programs and the amount of subsequent data increases. In addition to increasing use of wearables with wellness programs, a performance management trend towards more frequent performance evaluations (specifically among professional services and technology firms) provides an opportunity. A 2016 PwC Consumer Intelligence Series report found that 62% of consumers would find rewards for productivity improvements based on employer-monitored wearables to be useful. While companies like Vivametrica, Jiff, and Springbuk focus on cost reduction through lower health costs, Vulpine Analytics aims to increase employee productivity. Research shows that there is a meaningful relationship between wellness factors (sleep and exercise) and individual productivity. Vulpine Analytics will use this research to develop a model that integrates employee generated data to predict expected productivity. The model is refined with inputted data and is tailored to each employee in order to provide productivity boosting recommendations. Based on these trends and indicated demand, we will address the connection between personal health habits and productivity using employer-sponsored health and wellness programs and performance evaluations. The solution will include a dashboard providing employees with information and insight to help balance personal health and habits with their performance at work. By providing employees with a tool to help manage work-life balance, this will increase engagement in the wellness programs and generate more information to assist organizations in risk and cost reduction for insurance. At an employer level, the Vulpine Analytics platform will allow management to gain insight into aggregate level productivity, sleep, and overall wellness. Additionally, the analytic platform integrates performance evaluation data and draws correlations between employee productivity and performance (adjusted for role), allowing management to make smart decisions about their wellness programs and evaluation metrics.
Customer | HR Directors
Project Core Team: | Derek Gibbs, Eric Koek, Erika Nixon, David Yastremsky
Next Milestone: | Finish presentation, document data schema and processes, and finalize all deliverables.
Phase Status
| Status | Plan |  | Status | Plan |  | Status | Date
Analysis | G | 2017-02-16 | Testing | G | 2017-04-13
Design | G | 2017-03-02 | Selling / Presenting | G | 2017-04-25
Construction | G | 2017-04-07
Leading Indicators | Status |  |  | Status |  |  | Status
On-Time | G | On-Budget |  | G | Delivery to Scope |  | G
Major Accomplishments/Decisions
We developed the user interface and mobile prototype. We created a use case for the typical way our tool would be used. We will use it to showcase the prototype during the presentation. The pro forma was finalized. We determined the key components of our proprietary algorithm. We shifted from a full-featured wellness program to a productivity add-on for existing wellness programs. We shifted to a software as a service (SaaS) model. We determined the enterprise architecture.
CURRENT KEY ACTIVITIES --- NOTE ACTUAL (VS PROJECTED) DATES ARE INDICATED BY ITALICS
|  |  |  | START |  |  | END
Current Key Activities | STATUS |  | PHASE | PLAN | ACT | Comments | PLAN | ACT
Research functionality | G | Analysis |  | 2017-01-30 | 2017-01-30 | Redefining project resulted in additional need for analysis. | 2017-02-09 | 2017-02-09
Research competition | G | Analysis |  | 2017-01-30 | 2017-01-30 | Redefining project resulted in additional need for analysis. | 2017-02-09 | 2017-02-16
Finalize project | G | Analysis |  | 2017-02-09 | 2017-02-09 | Refined business idea | 2017-02-16 | 2017-02-16
Create near-completed charter | G | Analysis |  | 2017-02-03 | 2017-02-16 | Built on report feedback | 2017-03-02 | 2017-03-02
UI Mockup | G | Design |  | 2017-02-23 | 2017-03-02 | Created Tableau dashboard | 2017-03-02 | 2017-03-09
Determine data needs | G | Design |  | 2017-03-02 | 2017-03-02 |  | 2017-03-16 | 2017-03-23
Create project documents | G | Design |  | 2017-02-23 | 2017-02-23 |  | 2017-03-16 | 2017-04-12
Create prototype | G | Construction |  | 2017-02-28 | 2017-02-28 |  | 2017-04-07 | 2017-04-13
Contact project mentor | G | Feedback |  | 2017-03-09 | 2017-03-09 |  | 2017-04-07 | 2017-03-22
Test prototype | G | Testing |  | 2017-04-07 | 2017-04-12 |  | 2017-04-13 | 2017-04-13
Second follow up with mentor | G | Feedback |  | 2017-04-03 | 2017-04-12 |  | 2017-04-13 | 2017-04-12
Finalize documents | Y | Selling / Presentation |  | 2017-03-23 | 2017-04-12 | Will collect feedback and refine. | 2017-04-13
Prepare presentation | G | Selling / Presentation |  | 2017-04-13 |  |  | 2017-04-25
Key Issues
Description |  | Status | Resolution/Update |  |  |  | Owner
Planned Accomplishments
We will create our presentation and finalize our presentation deliverables. We will incorporate feedback from the status update and practice run of the presentation into our final deliverable and presentation. We will refine the prototypes, presentation, and documents.