## Status Summary
Project Dashboard
Note: Project plan with original dates and actual dates should be attached. | [6 empty] | Date: | 2016-09-29
Project Name: | Secure-Ification | [5 empty] | Project Status: | Y
Project Description: | The problem is the lack of awareness of the security rrisks out there associated with the Internet of Things as well as the excess amount of security information for multiple technologies people carry nowadays. Customers may be overwhelmed with the amount of information regarding cyber security and may also not be aware of the options they have to help protect themselves from security risks. Additionally, many companies have a "bring your own device (BYOB)" policy that may compromise business IT security.
Customer | Small Businesses, Medium Businesses and Individuals
Project Core Team: | Sean Murray, Josh Sandoe, Anna Kim, Robin Hibbard, Mike Bonatsos
Next Milestone: | Designing the solution
Phase Status
| Status | Plan |  | Status | Plan |  | Status | Date
Analysis | Y | 2016-09-15 | Testing | R | 2016-11-01 | Overall | Y | 2016-09-15
Design | Y | 2016-09-15 | Installation | R | 2016-11-01
Construction | R | 2016-10-01
Leading Indicators | Status |  |  | Status |  |  | Status
On-Time | G | On-Budget |  | Y | Delivery to Scope |  | G
Major Accomplishments/Decisions
Completed availability chart for the team.
Completed the idea for the solution that we will be creating
Completed the responsibilty chart.
Completed the Project Charter.
Talked to David Schuff about meeting with meeting with a ITACS member
CURRENT KEY ACTIVITIES --- NOTE ACTUAL (VS PROJECTED) DATES ARE INDICATED BY ITALICS
|  |  |  | START |  |  | END
Current Key Activities | STATUS |  | PHASE | PLAN | ACT | Comments | PLAN | ACT
Project Plan | G | Planning |  | 2016-09-06 | 2016-09-15 |  | 2016-09-17 | 2016-09-17
Proposal | G | Planning |  | 2016-09-08 | 2016-09-08
Project Charter | Y | Planning |  | 2016-09-06 | 2016-09-15 | Can change periodically throughout the project | 2016-09-17 | 2016-09-28
Scope | Y | Planning |  | 2016-09-06 | 2016-09-15 | Can change periodically throughout the project | 2016-09-17 | 2016-09-17
Budget | Y | Planning |  | 2016-09-19 | 2016-09-21 | Issues w/ numbers | 2016-09-20 | -
Idenitfy key features of solution | Y | Planning |  | 2016-09-20 | 2016-09-28 |  | 2016-09-26 | -
Design layout of dashboard | R | Planning |  | 2016-10-03 | - | Has not started | 2016-10-10 | -
Design layout of application | R | Planning |  | 2016-10-03 | - | Has not started | 2016-10-10 | -
Begin Prototyping | R | Execution |  | 2016-10-03 | - | Has not started | 2016-11-11 | -
Create the Community Site | R | Execution |  | 2016-10-03 | - | Has not started | 2016-11-11 | -
Meeting with ITACS representative | R | Planning |  | TBD
Key Issues
Description |  | Status | Resolution/Update |  |  |  | Owner
Availability for Group Meetings |  | G | Created an availability chart. |  |  |  | Group
Meeting with our Mentor |  | Y | We currently do not know who this person is so we cannot get receive feedback. |  |  |  | Project Sponsor
Getting Metrics |  | Y | Figuring out our baseline metrics |  |  |  | Robin
Communicating with the customers |  | R | Getting the customers to understand the purpose of the solution |  |  |  | Josh
Planned Accomplishments
This week we have made changes to the Project charter.We have began discussing and developing our idea for the design of the solutions we will be providing. In the next 2 weeks we will begin to sketch the layout of the dashboard and mobile application we will be creating.
Note on B47: Key Issues are issues that need your CM Director-level understanding and awareness.