## Status Summary
Project Dashboard
Note: Project plan with original dates and actual dates should be attached. | [6 empty] | Date: | 2016-10-19
Project Name: | PROtect | [5 empty] | Project Status: | Y
Project Description: | The problem is the lack of awareness of the security risks out there associated with the Internet of Things as well as the excess amount of security information for multiple technologies people carry nowadays. Customers may be overwhelmed with the amount of information regarding cyber security and may also not be aware of the options they have to help protect themselves from security risks. Additionally, many companies have a "bring your own device (BYOB)" policy that may compromise business IT security.
Customer | Small Businesses, Medium Businesses, and Individuals
Project Core Team: | Sean Murray, Josh Sandoe, Anna Kim, Robin Hibbard, Mike Bonatsos
Next Milestone: | Designing the solution, refining our value proposition and drafting prototype
Phase Status
| Status | Plan |  | Status | Plan |  | Status | Date
Analysis | Y | 2016-09-15 | Testing | R | 2016-11-01 | Overall | Y | 2016-09-15
Design | Y | 2016-09-15 | Installation | R | 2016-11-01
Construction | Y | 2016-10-20
Leading Indicators | Status |  |  | Status |  |  | Status
On-Time | Y | On-Budget |  | Y | Delivery to Scope |  | G
Major Accomplishments/Decisions
Completed the Project Charter.
Completed the idea for the solution that we will be creating
Initiated contact with a ITACS member
Initiated contact with Mentor
Begin Prototyping
CURRENT KEY ACTIVITIES --- NOTE ACTUAL (VS PROJECTED) DATES ARE INDICATED BY ITALICS
|  |  |  | START |  |  | END
Current Key Activities | STATUS |  | PHASE | PLAN | ACT | Comments | PLAN | ACT
Project Plan | G | Planning |  | 2016-09-06 | 2016-09-15 | Finished | 2016-09-17 | 2016-09-17
Proposal | G | Planning |  | 2016-09-08 | 2016-09-08 | Finished | 2016-09-08 | 2016-09-08
Project Charter | G | Planning |  | 2016-09-06 | 2016-09-15 | Can change periodically throughout the project | 2016-09-17 | 2016-09-28
Scope | Y | Planning |  | 2016-09-06 | 2016-09-15 | Can change periodically throughout the project | 2016-09-17 | 2016-09-17
Budget | Y | Planning |  | 2016-09-19 | 2016-09-21 | Issues w/ numbers | 2016-09-20 | -
Idenitfy key features of solution | Y | Planning |  | 2016-09-20 | 2016-09-28 | Have Started | 2016-09-26 | -
Design layout of dashboard | Y | Planning |  | 2016-10-03 | 2016-10-19 | Have Started | 2016-10-10 | -
Design layout of application | Y | Planning |  | 2016-10-03 | 2016-10-19 | Have Started | 2016-10-10 | -
Begin Prototyping | Y | Execution |  | 2016-10-03 | 2016-10-19 | Has not started | 2016-11-11 | -
Create the Community Site | R | Execution |  | 2016-10-03 |  | Has not started | 2016-11-11 | -
Meeting with ITACS representative | Y | Planning |  | 2016-10-05 |  | TBD
Key Issues
Description |  | Status | Resolution/Update |  |  |  | Owner
Availability for Group Meetings |  | G | Created an availability chart. |  |  |  | Group
Meeting with our Mentor |  | Y | We are having trouble finding a good time to meet with our mentor. There have been miscommunications and misunderstandings when trying to arrange a meeting. Working out the issues now on both ends. Potential meeting in the works for October 27th. |  |  |  | Project Sponsor
Getting Metrics |  | Y | Figuring out our baseline metrics |  |  |  | Robin
Communicating with the customers |  | R | Getting the customers to understand the purpose of the solution |  |  |  | Josh
Meeting ITACS Consultant |  | Y | We are having trouble finding a good time to meet with our ITACS Consultant. |  |  |  | Josh
Planned Accomplishments
Begin to sketch the layout of the dashboard and mobile application, and begin a draft of the prototype. Resolve the communication issues with mentor, and conduct a successful meeting.
Note on B47: Key Issues are issues that need your CM Director-level understanding and awareness.