## Status Summary
Project Dashboard
Note: Project plan with original dates and actual dates should be attached. | [6 empty] | Date: | 2016-11-10
Project Name: | PROtect | [5 empty] | Project Status: | Y
Project Description: | The problem is the lack of awareness of the security risks out there associated with the Internet of Things as well as the excess amount of security information for multiple technologies people carry nowadays. Customers may be overwhelmed with the amount of information regarding cyber security and may also not be aware of the options they have to help protect themselves from security risks. Additionally, many companies have a "bring your own device (BYOB)" policy that may compromise business IT security.
Customer | Small Businesses and Medium Businesses
Project Core Team: | Sean Murray, Josh Sandoe, Anna Kim, Robin Hibbard, Mike Bonatsos
Next Milestone: | Designing the solution, refining our value proposition and drafting prototype
Phase Status
| Status | Plan |  | Status | Plan |  | Status | Date
Analysis | Y | 2016-09-15 | Testing | R | 2016-11-01 | Overall | Y | 2016-09-15
Design | Y | 2016-09-15 | Installation | R | 2016-11-01
Construction | Y | 2016-10-20
Leading Indicators | Status |  |  | Status |  |  | Status
On-Time | Y | On-Budget |  | Y | Delivery to Scope |  | G
Major Accomplishments/Decisions
Met with ITACS consultant.
Began website creation.
Met with Mentor.
First prototype of mobile app complete.
Initiated dashboard prototype
CURRENT KEY ACTIVITIES --- NOTE ACTUAL (VS PROJECTED) DATES ARE INDICATED BY ITALICS
|  |  |  | START |  |  | END
Current Key Activities | STATUS |  | PHASE | PLAN | ACT | Comments | PLAN | ACT
Project Plan | G | Planning |  | 2016-09-06 | 2016-09-15 | Finished | 2016-09-17 | 2016-09-17
Proposal | G | Planning |  | 2016-09-08 | 2016-09-08 | Finished | 2016-09-08 | 2016-09-08
Project Charter | G | Planning |  | 2016-09-06 | 2016-09-15 | Can change periodically throughout the project | 2016-09-17 | 2016-09-28
Scope | Y | Planning |  | 2016-09-06 | 2016-09-15 | Can change periodically throughout the project | 2016-09-17 | 2016-09-17
Budget | Y | Planning |  | 2016-09-19 | 2016-09-21 | Determining labor costs and logistics. | 2016-09-20 | -
Idenitfy key features of solution | Y | Planning |  | 2016-09-20 | 2016-09-28 | Finished | 2016-09-26 | 2016-11-01
Design layout of dashboard | Y | Planning |  | 2016-10-03 | 2016-10-19 | Have Started | 2016-10-10 | -
Design layout of application | Y | Planning |  | 2016-10-03 | 2016-10-19 | Finished -may change periodically | 2016-10-10 | 2016-11-03
Begin Prototyping | Y | Execution |  | 2016-10-03 | 2016-10-19 | Started | 2016-11-11 | -
Create the Community Site | Y | Execution |  | 2016-10-03 |  | Can change periodically throughout the project | 2016-11-11 | 2016-11-08
Meeting with ITACS representative | G | Planning |  | 2016-10-05 |  | Finished |  | 2016-10-26
Key Issues
Description |  | Status | Resolution/Update |  |  |  | Owner
Availability for Group Meetings |  | G | Created an availability chart. |  |  |  | Group
Meeting with our Mentor |  | G | Met with our mentor as a group and received feedback. Planning another meeting. |  |  |  | Project Sponsor
Getting Metrics |  | Y | Figuring out our baseline metrics. Meeting with our ITACS consultant has helped. |  |  |  | Robin
Communicating with the customers |  | R | Getting the customers to understand the purpose of the solution |  |  |  | Josh
Meeting ITACS Consultant |  | G | Have met and received valuable information from our ITACS Consultant. |  |  |  | Josh
Designing Dashboard |  | R | Difficulty designing dashboard and integrating metrics into design. |  |  |  | Sean
Planned Accomplishments
Meet in person with the group to work on dashboard design and working on how to integrate metrics into dashboard. Will also plan on integrating the material our ITACS consultant shared with us. Finalize mobile app prototype and begin dashboard prototype. Schedule a video or in-person meeting with Mentor as well as demonstrate our prototypes and gain feedback.
Note on B47: Key Issues are issues that need your CM Director-level understanding and awareness.