From: Quy Le, Louisa Carleton, Jonathan Kerr

To: Mart Doyle

Subject: Weekly Progress Report – September 20, 2016

Period: 10/10/16-10/13/16

Hours:  2    Hours to Date: 9

Accomplishments for October 13, 2016

- Quy, Jon, Louisa, Hassan, Khaled, Raphael, and Yan met up to discuss necessary tasks that must be done before the next meeting. (Speak to project advisor)

- Khaled, Hassan, Raphael, and Yan presented critical design review. Quy, Jon, Louisa were also present. Got feedback from advisors about what needed to be changed.

Goals for October 21, 2016

- Revise Project Schedule based on feedback from advisors

- Begin testing

- Get questions about best testing approach from advisor

Issues:

- There was a lot of miscommunication between advisors

- We are unsure which tests we will perform now due to feedback from critical design review

- Due to feedback, we may need more tests along with different ratios for mixtures

- Difficulty getting a meeting scheduled with direct advisor

- Conflicting advice from advisors