## Status Summary
Project Dashboard
Note: Project plan with original dates and actual dates should be attached. | [6 empty] | Date: | 2016-04-11
Project Name: | Reduce Freebooting | [5 empty] | Project Status: | Y
Project Description: | Info from project charter
Customer | Content creators on YouTube
Project Core Team: | Noah Berson, Joe Derer, Aaron Ploucher
Next Milestone: | Finalizing prototype
Phase Status
| Status | Plan |  | Status | Plan |  | Status | Date
Analysis | G | 2015-02-23 | Testing | Y | 2016-04-08
Design | G | 2016-03-15 | Installation | Y | 2016-04-15
Construction | G | 2016-04-01
Leading Indicators | Status |  |  | Status |  |  | Status
On-Time | Y | On-Budget |  | G | Delivery to Scope |  | G
Major Accomplishments/Decisions
We finished and uploaded our deliverables to our project website. We are also in the last stages of our prototype. We mapped out our presentation.
CURRENT KEY ACTIVITIES --- NOTE ACTUAL (VS PROJECTED) DATES ARE INDICATED BY ITALICS
|  |  |  | START |  |  | END
Current Key Activities | STATUS |  | PHASE | PLAN | ACT | Comments | PLAN | ACT
Test plan | Y | Design |  | 2016-03-08 | 2016-03-15
Final project plan | G | Analysis |  | 2016-02-16 | 2016-02-23
Final Presentation | Y | Analysis |  | 2016-04-05 | 2016-04-17
Final Prototype | Y | Installation |  | 2016-04-10 | 2016-04-17
Key Issues
Description |  | Status | Resolution/Update |  |  |  | Owner
Prototype |  | Y | We were at a crossroads with a website or a JustinMind prototype. |  |  |  | Aaron
We chose to do both.
Planned Accomplishments
We plan on finishing up the website and prototype while also cleaning up our project community site. We plan on also finalizing the presentation by 4/17.
Note on B46: Key Issues are issues that need your CM Director-level understanding and awareness.