## Status Summary
Project Dashboard
Note: Project plan with original dates and actual dates should be attached. | [6 empty] | Date: | 2016-02-16
Project Name: | Reduce Freebooting | [5 empty] | Project Status: | Y
Project Description: | Info from project charter
Customer | Content creators on YouTube
Project Core Team: | Noah Berson, Joe Derer, Aaron Ploucher.
Next Milestone: | Begin basic prototype
Phase Status
| Status | Plan |  | Status | Plan |  | Status | Date
Analysis | G | 2016-02-23 | Testing | G | 2016-04-08
Design | Y | 2016-03-15 | Installation | G | 2016-04-15
Construction | G | 2016-04-01
Leading Indicators | Status |  |  | Status |  |  | Status
On-Time | Y | On-Budget |  | G | Delivery to Scope |  | G
Major Accomplishments/Decisions
Began working on a realistic budget. Finished up the analysis stage with everything we want in the prototype and went through a very basic outline of the potential make-up of the site.
CURRENT KEY ACTIVITIES --- NOTE ACTUAL (VS PROJECTED) DATES ARE INDICATED BY ITALICS
|  |  |  | START |  |  | END
Current Key Activities | STATUS |  | PHASE | PLAN | ACT | Comments | PLAN | ACT
Test plan | Y | Design |  | 2016-03-08 | 2016-03-15
Final project plan | Y | Analysis |  | 2016-02-16 | 2016-02-23
Key Issues
Description |  | Status | Resolution/Update |  |  |  | Owner
Spring Break is coming up |  | G | With our project still in it's beginning stages and with about 2 and a |  |  |  | Joe
half more months of work, a week off shouldn't mess up anything
Planned Accomplishments
Relax during spring break. Come back with more ideas for the prototype.
Note on B46: Key Issues are issues that need your CM Director-level understanding and awareness.