## Status Summary
Project Dashboard
Note: Project plan with original dates and actual dates should be attached. | [6 empty] | Date: | 2016-02-09
Project Name: | Reduce Freebooting | [5 empty] | Project Status: | Y
Project Description: | Info from project charter
Customer | Content Creators on YouTube
Project Core Team: | Noah Berson, Joe Derer, Aaron Ploucher
Next Milestone: | Project Schedule
Phase Status
| Status | Plan |  | Status | Plan |  | Status | Date
Analysis | Y | 2016-02-23 | Testing | G | 2016-04-08
Design | Y | 2016-03-15 | Installation | G | 2016-04-15
Construction | G | 2016-04-01
Leading Indicators | Status |  |  | Status |  |  | Status
On-Time | Y | On-Budget |  | Y | Delivery to Scope |  | Y
Major Accomplishments/Decisions
Project Charter was finalized. We moved into the analysis stage as we began talks of how the site will be constructed and what it will offer in terms of usefulness.
CURRENT KEY ACTIVITIES --- NOTE ACTUAL (VS PROJECTED) DATES ARE INDICATED BY ITALICS
|  |  |  | START |  |  | END
Current Key Activities | STATUS |  | PHASE | PLAN | ACT | Comments | PLAN | ACT
Test plan | G | Design |  | 2016-03-08 | 2016-03-15
Final project plan | Y | Analysis |  | 2016-02-16 | 2016-02-23
Key Issues
Description |  | Status | Resolution/Update |  |  |  | Owner
Planned Accomplishments
Get the project web site up an runnning.
Note on B46: Key Issues are issues that need your CM Director-level understanding and awareness.