## Status Summary
Project Dashboard
Note: Project plan with original dates and actual dates should be attached. | [6 empty] | Date: | 2016-03-08
Project Name: | Reduce Freebooting | [5 empty] | Project Status: | Y
Project Description: | Info from project charter
Customer | Content creators on YouTube
Project Core Team: | Noah Berson, Joe Derer, Aaron Ploucher
Next Milestone: | Updating Project Website
Phase Status
| Status | Plan |  | Status | Plan |  | Status | Date
Analysis | G | 2015-02-23 | Testing | Y | 2016-04-08
Design | G | 2016-03-15 | Installation | Y | 2016-04-15
Construction | Y | 2016-04-01
Leading Indicators | Status |  |  | Status |  |  | Status
On-Time | Y | On-Budget |  | G | Delivery to Scope |  | Y
Major Accomplishments/Decisions
We mapped out the final layout for our project website. Now we need to work on/finish the deliverables for upload.
CURRENT KEY ACTIVITIES --- NOTE ACTUAL (VS PROJECTED) DATES ARE INDICATED BY ITALICS
|  |  |  | START |  |  | END
Current Key Activities | STATUS |  | PHASE | PLAN | ACT | Comments | PLAN | ACT
Test plan | Y | Design |  | 2016-03-08 | 2016-03-15
Final project plan | G | Analysis |  | 2016-02-16 | 2016-02-23
Key Issues
Description |  | Status | Resolution/Update |  |  |  | Owner
Planned Accomplishments
We are trying to work on the protoype and knocking out all of the layouts.
Note on B46: Key Issues are issues that need your CM Director-level understanding and awareness.