## Status Summary
Project Dashboard
Note: Project plan with original dates and actual dates should be attached. | [6 empty] | Date: | 2016-02-02
Project Name: | Reduce Freebooting | [5 empty] | Project Status: | G
Project Description: | Info from project charter
Customer | Content creators on YouTube
Project Core Team: | Noah Berson, Joe Derer, Aaron Ploucher
Next Milestone: | Iron out the project charter
Phase Status
| Status | Plan |  | Status | Plan |  | Status | Date
Analysis | G | 2016-02-23 | Testing | G | 2016-04-08
Design | G | 2016-03-15 | Installation | G | 2016-04-15
Construction | G | 2016-04-01
Leading Indicators | Status |  |  | Status |  |  | Status
On-Time | G | On-Budget |  | G | Delivery to Scope |  | G
Major Accomplishments/Decisions
Last week, we came up with our idea and ironed out a plan for moving forward. We would create a prototype of a GIF social networking site with the main objective of reducing freebooting from content creators on YouTube. It would eventually branch out into a full blown social networking site for all users, not just content creators.
CURRENT KEY ACTIVITIES --- NOTE ACTUAL (VS PROJECTED) DATES ARE INDICATED BY ITALICS
|  |  |  | START |  |  | END
Current Key Activities | STATUS |  | PHASE | PLAN | ACT | Comments | PLAN | ACT
Project Scope | G | Design |  | 2016-03-08 | 2016-03-15
Status Reports | G | Analysis |  | 2005-02-16 | 2016-02-23
Key Issues
Description |  | Status | Resolution/Update |  |  |  | Owner
Planned Accomplishments
Next week we are meeting to discuss how we will divide up all of our objectives. We also have to create and finish our charter and update a new status report.
Note on B46: Key Issues are issues that need your CM Director-level understanding and awareness.