## Status Summary
Project Dashboard
[7 empty] | Date: | 2016-04-13
Project Name: | Patience | [5 empty] | Project Status: | G
Project Description: | Cost of health care in the US is sky rocketing-this is partially due to the medical wording of health care information and documents. The average American reads at a 5th grade reading level while health care documents are written at the collegiate level. This project will ‘translate’ the academic language of health care documents into common day speak. This makes health care documents more accessible to the average American, increasing individual understanding of health care and health related information. With increased understanding and awareness patients are more likely to take the necessary steps to take care of their bodies, treat their aliments, and prevent worsening health conditions. Ultimately this reduces the cost and increases the quality of health care.
Customer | Private medical practices
Project Core Team: | Ben Kates, Leigh McKenzie, Ciara Murphy
Next Milestone: | Completion of prototype
Phase Status
| Status | Plan |  | Status | Plan |  | Status | Date
Analysis | G | 2016-02-11 | Testing | G | 2016-04-06
Design | G | 2016-02-25 | Installation | G | 2016-04-20
Construction | G | 2016-03-07
Leading Indicators | Status |  |  | Status |  |  | Status
On-Time | G | On-Budget |  | G | Delivery to Scope |  | G
Major Accomplishments/Decisions
The project charter, website, prototype and presenation are all complete.
CURRENT KEY ACTIVITIES --- NOTE ACTUAL (VS PROJECTED) DATES ARE INDICATED BY ITALICS
|  |  |  | START |  |  | END
Current Key Activities | STATUS |  | PHASE | PLAN | ACT | Comments | PLAN | ACT
Final Charter | G | Design |  | 2016-02-03 | 2016-02-03 | Met with Munir | 2016-02-10 | 2016-02-10
Final project plan | G | Analysis |  | 2016-02-10 | 2016-02-10 | Review Meeting with Munir | 16--Mar
UI Mockup | G | Design |  | 2016-02-24 | 2016-02-24 | Begin Website | 16--Mar | 2016-03-20
Build Prototype | G | Execution |  | 1--Mar | 1--Mar | Begin Presentation | 16--Mar
Key Issues
Description |  | Status | Resolution/Update |  |  |  | Owner
Need to verify subscription to JustInMind |  | G | Verified the keys, we now all have access |  |  |  | Leigh McKenzie
Unable to contact Nancy Hunsberger |  | G | Contacting family friend who is a family doctor and/or Munir's contact in CA |  |  |  | Ben Kates, Ciara Murphy
Planned Accomplishments
The team will continue practicing presenation execution. Other than that all project deliverables have been completed.
Note on B40: Key Issues are issues that need your CM Director-level understanding and awareness.