## Status Summary
Project Dashboard
[7 empty] | Date: | 2016-01-27
Project Name: | Patience | [5 empty] | Project Status: | Y
Project Description: | Cost of health care in the US is sky rocketing-this is largely due to the academic wording of health care information and documents. The average American reads at a 5th grade reading level while health care documents are written on a highly collegiate level. This project will ‘translate’ the academic language of health care documents into common day speak. This makes health care documents more accessible to the average American, increasing individual understanding of health care and health related information. Ultimately this reduces the cost and increases the quality of health care.
Customer | Nancy Hunsberger ¦ Director, Customer Support, Information Technology
Project Core Team: | Ben Kates, Leigh McKenzie, Ciara Murphy
Next Milestone: | Analysis of current processes
Phase Status
| Status | Plan |  | Status | Plan |  | Status | Date
Analysis | Y | 2016-02-11 | Testing | Y | 2016-04-06
Design | Y | 2016-02-25 | Installation | Y | 2016-04-20
Construction | Y | 2016-03-23
Leading Indicators | Status |  |  | Status |  |  | Status
On-Time | Y | On-Budget |  | Y | Delivery to Scope |  | Y
Major Accomplishments/Decisions
Decision to schedule an interview with Nancy and create relationships with her subordinates in order to identify processes in the critical path.
CURRENT KEY ACTIVITIES --- NOTE ACTUAL (VS PROJECTED) DATES ARE INDICATED BY ITALICS
|  |  |  | START |  |  | END
Current Key Activities | STATUS |  | PHASE | PLAN | ACT | Comments | PLAN | ACT
Test plan | Y | Design |  | 2016-02-03 | 2016-02-03 |  | 2016-02-10 | 2016-02-10
Final project plan | Y | Analysis |  | 2016-02-17 | 2016-02-17 |  | 2016-02-24 | 2016-02-24
UI Mockup | Y | Design |  | 2016-02-24 | 2016-02-24 |  | 2016-03-02 | 2016-03-02
Key Issues
Description |  | Status | Resolution/Update |  |  |  | Owner
Need to verify subscription to JustInMind |  | Y | Sent an email to customer support
Planned Accomplishments
Next week we are meeting with our project champion to gather her input and ideas. We will also scheduale meetings with other key stakeholders the champion indicates. After the meetings we will being further developing our prototype idea and developing our business case.
Note on B39: Key Issues are issues that need your CM Director-level understanding and awareness.