## Status Summary
Project Dashboard
Note: Project plan with original dates and actual dates should be attached. | [6 empty] | Date: | 2017-02-21
Project Name: | SpotaGuide | [5 empty] | Project Status: | G
Project Description: | Travellers who are unfamiliar with a city can acquire or create a personalized itinerary ahead of their visit. Locals will earn money by building, managing, and facilitating unique tours of the city’s best food and entertainment.
Customer | Tourists
Project Core Team: | Philip Tocci, Kevin Vong, Anthony Vu, Brian Wallace
Next Milestone: | Have a finished website and a blueprint of our prototype.
Phase Status
| Status | Plan |  | Status | Plan |  | Status | Date
Analysis | G | 2017-04-12 | Testing | R | 2017-03-28
Design | G | 2017-04-12 | Installation | R | 2017-04-12
Construction | Y | 2017-04-12
Leading Indicators | Status |  |  | Status |  |  | Status
On-Time | Y | On-Budget |  | G | Delivery to Scope |  | G
Major Accomplishments/Decisions
We have been continually revising our charter and also made a website for our project. The project website can be seen at - http://community.mis.temple.edu/spotaguide/
CURRENT KEY ACTIVITIES --- NOTE ACTUAL (VS PROJECTED) DATES ARE INDICATED BY ITALICS
|  |  |  | START |  |  | END
Current Key Activities | STATUS |  | PHASE | PLAN | ACT | Comments | PLAN | ACT
Project Charter | G | Revision |  | 2017-01-31 | 2017-02-07 |  | 2017-02-21 | 2017-02-21
Project Website | G | Development |  | 2017-02-07 | 2017-02-14 |  | 2017-02-28 | 2017-02-28
Key Issues
Description |  | Status | Resolution/Update |  |  |  | Owner
Project Website Development |  | Y | We are currently working to add content to our website and make it easily navigable. |  |  |  | All
Planned Accomplishments
We hope to have our website finished by next week. We will start thinking about other aspects of the project such as the prototype.
Note on B46: Key Issues are issues that need your CM Director-level understanding and awareness.