## Status Summary
Project Dashboard
Note: Project plan with original dates and actual dates should be attached. | [6 empty] | Date: | 2017-02-07
Project Name: | SpotaGuide | [5 empty] | Project Status: | G
Project Description: | Travellers who are unfamiliar with a city can acquire or create a personalized itinerary ahead of their visit. Locals will earn money by building, managing, and facilitating unique tours of the city’s best food and entertainment.
Customer | Tourists
Project Core Team: | Philip Tocci, Kevin Vong, Anthony Vu, Brian Wallace
Next Milestone: | Have a project website and revised charter.
Phase Status
| Status | Plan |  | Status | Plan |  | Status | Date
Analysis | G | 2017-04-12 | Testing | R | 2017-03-28
Design | G | 2017-04-12 | Installation | R | 2017-04-12
Construction | Y | 2017-04-12
Leading Indicators | Status |  |  | Status |  |  | Status
On-Time | Y | On-Budget |  | G | Delivery to Scope |  | G
Major Accomplishments/Decisions
Last week, we finished a rough draft of our charter and decided on the name of our application to be "SpotaGuide".
CURRENT KEY ACTIVITIES --- NOTE ACTUAL (VS PROJECTED) DATES ARE INDICATED BY ITALICS
|  |  |  | START |  |  | END
Current Key Activities | STATUS |  | PHASE | PLAN | ACT | Comments | PLAN | ACT
Project Charter | G | Revision |  | 2017-01-31 | 2017-02-07 |  | 2017-02-21 | 2017-02-21
Key Issues
Description |  | Status | Resolution/Update |  |  |  | Owner
Filling out Project Charter |  | Y | We were unsure of what we wanted to include in certain sections of the charter. |  |  |  | All
Planned Accomplishments
We hope to have our charter updated and will start working on the project website.
Note on B46: Key Issues are issues that need your CM Director-level understanding and awareness.